APROJECT FROM

LOCAL NGO-(MODRENEDUCATION FOR KURDISTAN)

| NAME OF THE PROJECT |  | NAME OF NGO: |
| --- | --- | --- |
| Supporting blind person right through opening for them Braille courses |  | MODREN EDUCATION FOR KURDISTAN |
| Bulged : |  | Contact information |
|  | 8600 00$ |  |  | Name: MR JWANRO MUSTAFA Addres: sleamnai city kurdistan region Iraq building of union of blinds person mobile:07730062006 e-mail: jwanroabdula@hotmail.com |
| Duration of the project: Two month |  | Location of the project: |
| from -10-20 -/2017 تاريخ النهاية: 20/21/2017 |  |  | Kurdistan region iraq SLEAMNAI CITY-HALABJA DISTRIC |

| The beneficiaries |
| --- |
|  | All the blinds person in Kurdistan |

1. summery

There are a large number of blind people in the Kurdistan Region and they have great suffering in various fields and their rights are constantly violated and therefore it is necessary that their demands be formulated clearly(pressure to achieve their demands for a decent living And one of the need assessment of the blind person opening Braille course for them in the fare area from the city

2. the goal of the project

Supporting blind right

3-the activities

first Hire a professional teachers in Braille teaching, and hire a hall in the district and inform the blinds in the district to participate in Braille languages Second Starting the course for three weeks and distributing Braille plate among the blind students to teaching on it Third: In the end of the course we will distributing certification for blinds students and plate Braille And five Braille printer to To six outstanding students

| -work plan |
| --- |
| 2 month | 1 month | الأنشطة و الفعاليات |
| W4 | W3 | W2 | W1 | W4 | W3 | W2 | W1 |  |
|  |  |  |  |  |  |  |  | Form a team and prepare and hire the teacher and the hall |
|  |  |  |  |  |  |  |  | Register the students |
|  |  |  |  |  |  |  |  | Start the course |
|  |  |  |  |  |  |  |  | Start the Braille course |
|  |  |  |  |  |  |  |  | Start the Braille course |
|  |  |  |  |  |  |  |  | Distributing certification writing the final report |
|  |  |  |  |  |  |  |  | Finance report) |

| - Initiative budget |
| --- |
| total $ | coast $ | المدة \ الوحدة | الكمية \ الوحدة | item | ت |
|  |  | time | duration |  | number |  |  |
| 400 | 200 | month | 2 | person | 1 | manager | 1 |
| 800 | 100 | month | 2 | person | 4 | monitor |  |
| 300 | 150 | month | 1 | Person | 2 | Make contract with two teacher for one month | 2 |
| 100 | 50 | month | 2 | Mobile cart |  | communication | 3 |
| 400 | 10 | month | 1 | person | 40 | Write the manual | 4 |
| 500 | 500 | month | 1 | number | 1 | Hire a hall | 5 |
| 300 | 300 | month | 1 | person | 1 | refreshment | 6 |
| 600 | 600 | month | 1 | number | 1 | Transportation for the blind students to the hall | 7 |
| 200 | 100 | 2 month | 1 | program | 1 | copy | 8 |
| 300$ |  |  |  |  |  | STATIONARIES |  |
| 1100 | 50$ |  |  |  | 22 number | Braille plate |  |
| 3000 | 600 |  |  |  | 5 | Braille printer |  |
| 400 | 200 | 2month | 1 | program | 1 | Administration cost | 9 |
| 200 | 100 | month | 2 | person | 1 | accountant | 10 |
| 8600$ | المجموع |