## DEE Wise ACRs
RAJIV VIDYA MISSION (SSA) - PRAKASAM DISTRICT.
PROGRESS REPORT FOR ACRs SANCTIONED UNDER SSA 2012-13 as on 31-3-2013
Name of the Constituency
Sl. No | Name of the Mandal | Revenue Division | Constituency Wise | DEE Wise | AEE Wise | Name of the School | Category | Rural / Urban | No of ACRs | Estimate Cost (Rs.in Lakhs) | Stage of work | [10 empty] | Remarks
[11 empty] | FL | BL | LL | RL | Roof Laid | Comp leted | Not Started | To be Cancelled
1 | ADDANKI | ONGOLE | ADDANKI | ADDANKI | P.Venkateswarlu | 0816005 - MPPS VEMPARALA AA | PS | Urban | 1 | [6 empty] | 1 |  |  | 1 | 0
2 | ADDANKI | ONGOLE | ADDANKI | ADDANKI | P.Venkateswarlu | 0816006 - MPPS CHINAKOTHA PALLI SC | PS | Urban | 1 |  |  | 1 | [6 empty] | 1 | 0
3 | ADDANKI | ONGOLE | ADDANKI | ADDANKI | P.Venkateswarlu | 0816008 - MPPS GOVADA SC | PS | Urban | 1 |  |  | 1 | [6 empty] | 1 | 0
4 | ADDANKI | ONGOLE | ADDANKI | ADDANKI | P.Venkateswarlu | 0816012 - MPPS DHARMAVARAM HC | PS | Urban | 1 | [7 empty] | 1 |  | 1 | 0 |  | Dismantling
5 | ADDANKI | ONGOLE | ADDANKI | ADDANKI | P.Venkateswarlu | 0816022 - MPPS GOPALAPURAM ST | PS | Urban | 1 |  |  | 1 | [6 empty] | 1 | 0
6 | ADDANKI | ONGOLE | ADDANKI | ADDANKI | P.Venkateswarlu | 0816063 - MPPS NTR COLONY | PS | Urban | 1 | [6 empty] | 1 |  |  | 1 | 0
7 | ADDANKI | ONGOLE | ADDANKI | ADDANKI | P.Venkateswarlu | 0816067 - MPPS CHEKRAYAPALEM KMP | PS | Urban | 1 |  |  |  |  | 1 |  |  |  |  | 1 | 0
8 | ADDANKI | ONGOLE | ADDANKI | ADDANKI | P.Venkateswarlu | 0816302 - MPUPS VEMPARALA | UPS | Urban | 2 |  |  | 2 | [6 empty] | 2 | 0
9 | ADDANKI | ONGOLE | ADDANKI | ADDANKI | P.Venkateswarlu | 0816310 - MPUPS MODEPALLI | UPS | Urban | 1 |  | 1 | [7 empty] | 1 | 0
10 | ADDANKI | ONGOLE | ADDANKI | ADDANKI | P.Venkateswarlu | 0816319 - MPUPS KOTOKALAPUDI | UPS | Urban | 2 |  |  |  |  | 2 |  |  |  |  | 2 | 0
11 | ADDANKI | ONGOLE | ADDANKI | ADDANKI | P.Venkateswarlu | 0816010 - MPPS SRINIVASA NAGAR | PS | Urban | 1 |  |  | 1 | [6 empty] | 1 | 0
12 | ADDANKI | ONGOLE | ADDANKI | ADDANKI | P.Venkateswarlu | 0816015 - MPPS GOLLAPALEM | PS | Urban | 1 |  |  |  | 1 | [5 empty] | 1 | 0
13 | ADDANKI | ONGOLE | ADDANKI | ADDANKI | P.Venkateswarlu | 0816023 - MPPS GOPALAPURAM SC | PS | Urban | 1 |  |  | 1 | [6 empty] | 1 | 0
14 | ADDANKI | ONGOLE | ADDANKI | ADDANKI | P.Venkateswarlu | 0816036 - MPPS RALLAPALLI | PS | Urban | 1 |  |  | 1 | [6 empty] | 1 | 0
15 | ADDANKI | ONGOLE | ADDANKI | ADDANKI | P.Venkateswarlu | 0816044 - MPPS RAMAKRISHNA PURAM | PS | Urban | 1 | [7 empty] | 1 |  | 1 | 0 |  | Dismantling
16 | ADDANKI | ONGOLE | ADDANKI | ADDANKI | P.Venkateswarlu | 0816066 - GOVT PS YANADI COLONY | PS | Urban | 1 |  |  | 1 | [6 empty] | 1 | 0
17 | ADDANKI | ONGOLE | ADDANKI | ADDANKI | P.Venkateswarlu | 0816602 - ZPHS CHEKRAYA PALEM |  |  | 2 |  |  |  |  | 2
18 | ADDANKI | ONGOLE | ADDANKI | ADDANKI |  | 0816302 - MPUPS VEMPARALA |  |  | 1 |  |  | 1
19 | ADDANKI | ONGOLE | ADDANKI | ADDANKI |  | 0816307 - MPUPS NAGULAPADU |  |  | 1 | [7 empty] | 1
| ADDANKI | [7 empty] | 22 | 0 | 1 | 10 | 1 | 5 | 0 | 2 | 3 | 0 | 18 | 0 | 0
20 | ARDHAVEEDU | MARKAPUR | GIDDALUR | KANIGIRI |  | 0808006 - MPPS KAKARLA | PS | Rural | 2 |  |  |  | 2
21 | ARDHAVEEDU | MARKAPUR | GIDDALUR | KANIGIRI |  | 0808009 - MPPS SANKARAPURAM | PS | Rural | 1 |  |  | 1
22 | ARDHAVEEDU | MARKAPUR | GIDDALUR | KANIGIRI |  | 0808028 - MPPS PAPINENI PALLI (U) | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | Dismantling
23 | ARDHAVEEDU | MARKAPUR | GIDDALUR | KANIGIRI |  | 0808034 - MPPS NAGULAVARAM BC | PS | Rural | 1 |  |  | 1
24 | ARDHAVEEDU | MARKAPUR | GIDDALUR | KANIGIRI |  | 0808302 - MPUPS BOMMILINGAM | UPS | Rural | 2 |  |  | 2
25 | ARDHAVEEDU | MARKAPUR | GIDDALUR | KANIGIRI |  | 0808304 - MPUPS MAGUTURU | UPS | Rural | 2 |  | 2
26 | ARDHAVEEDU | MARKAPUR | GIDDALUR | KANIGIRI |  | 0808308 - MPUPS MOHIDDINPURAM | UPS | Rural | 1 |  |  | 1
27 | ARDHAVEEDU | MARKAPUR | GIDDALUR | KANIGIRI |  | 0808004 - MPPS BASIREDDY PALLI | PS | Rural | 1 |  | 1
28 | ARDHAVEEDU | MARKAPUR | GIDDALUR | KANIGIRI |  | 0808012 - MPPS PEDAKANDUKURU ST | PS | Rural | 1 |  |  | 1
| ARDHAVEEDU | [7 empty] | 12 | 0 | 3 | 6 | 2 | 0 | 0 | 0 | 1 | 0
29 | B.PETA | MARKAPUR | GIDDALUR | KANIGIRI |  | 0833010 - MPPS,BESTAVARIPETA | PS | Rural | 1 | [5 empty] | 1
30 | B.PETA | MARKAPUR | GIDDALUR | KANIGIRI |  | 0833021 - MPPS,RETLA PALLI | PS | Rural | 1 |  |  | 1
31 | B.PETA | MARKAPUR | GIDDALUR | KANIGIRI |  | 0833043 - MPPS,CHENNUPALLI | PS | Rural | 1 |  |  | 1
32 | B.PETA | MARKAPUR | GIDDALUR | KANIGIRI |  | 0833302 - MPUPS,J.C.AGRAHARAM | UPS | Rural | 1 |  |  | 1
33 | B.PETA | MARKAPUR | GIDDALUR | KANIGIRI |  | 0833308 - MPUPS,KOTHA MALLAPURAM | UPS | Rural | 1 |  |  | 1
34 | B.PETA | MARKAPUR | GIDDALUR | KANIGIRI |  | 0833023 - MPPS,J.C.AGRAHARAM | PS | Rural | 1 |  |  |  | 1
35 | B.PETA | MARKAPUR | GIDDALUR | KANIGIRI |  | 0833041 - MPPS,HANUMAYA PALLI | PS | Rural | 1 |  |  | 1
36 | B.PETA | MARKAPUR | GIDDALUR | KANIGIRI |  | 0833048 - MPPS,POGULLA | PS | Rural | 1 | [5 empty] | 1
| B.PETA | [7 empty] | 8 | 0 | 0 | 5 | 1 | 0 | 2 | 0 | 0 | 0
20 | BALLIKURUVA | ONGOLE | ADDANKI | ADDANKI | P.Venkateswarlu | 0817004 - MPPS SOMAVARAPPADU | PS | Rural | 1 | [6 empty] | 1 |  |  | 1 | 0
21 | BALLIKURUVA | ONGOLE | ADDANKI | ADDANKI | P.Venkateswarlu | 0817006 - MPPS VEMAVARAM | PS | Rural | 2 | [6 empty] | 2 |  |  | 2 | 0
22 | BALLIKURUVA | ONGOLE | ADDANKI | ADDANKI | P.Venkateswarlu | 0817008 - MPPS GANGAPALEM | PS | Rural | 1 |  |  |  | 1 | [5 empty] | 1 | 0
23 | BALLIKURUVA | ONGOLE | ADDANKI | ADDANKI | P.Venkateswarlu | 0817016 - MPPS BALLIKURAVA NR CHURCH | PS | Rural | 1 | [6 empty] | 1 |  |  | 1 | 0
24 | BALLIKURUVA | ONGOLE | ADDANKI | ADDANKI | P.Venkateswarlu | 0817020 - MPPS SUJATHANAGAR CLY | PS | Rural | 1 | [6 empty] | 1 |  |  | 1 | 0
25 | BALLIKURUVA | ONGOLE | ADDANKI | ADDANKI | P.Venkateswarlu | 0817034 - MPPS KUKATLA PALLI (HC) | PS | Rural | 2 |  |  | 2 | [6 empty] | 2 | 0
26 | BALLIKURUVA | ONGOLE | ADDANKI | ADDANKI | P.Venkateswarlu | 0817036 - MPPS GORRE PADU | PS | Rural | 1 | [6 empty] | 1 |  |  | 1 | 0
27 | BALLIKURUVA | ONGOLE | ADDANKI | ADDANKI | P.Venkateswarlu | 0817038 - MPPS VELAMAVARI P. (HE) | PS | Rural | 1 |  |  | 1 | [6 empty] | 1 | 0
28 | BALLIKURUVA | ONGOLE | ADDANKI | ADDANKI | P.Venkateswarlu | 0817039 - MPPS VELAMAVARI P. (HC) | PS | Rural | 1 |  |  | 1 | [6 empty] | 1 | 0
29 | BALLIKURUVA | ONGOLE | ADDANKI | ADDANKI | P.Venkateswarlu | 0817043 - MPPS VALLAPALLI, | PS | Rural | 1 |  |  | 1 | [6 empty] | 1 | 0
30 | BALLIKURUVA | ONGOLE | ADDANKI | ADDANKI | P.Venkateswarlu | 0817044 - MPPS KOMMINENI VARI PALEM | PS | 1 | 1 |  |  | 1 | [6 empty] | 1 | 0
| BALLIKURUVA | [7 empty] | 13 | 0 | 0 | 6 | 1 | 0 | 0 | 6 | 0 | 0
48 | C.S.PURAM | KANDUKUR | KANIGIRI | KANIGIRI |  | 0838015 - MPPS,YEKUNAM PURAM | PS | Rural | 1 |  |  | 1
49 | C.S.PURAM | KANDUKUR | KANIGIRI | KANIGIRI |  | 0838017 - MPPS,KRISHNAMNAYUNI PALLI | PS | Rural | 1 |  |  |  |  | 1
50 | C.S.PURAM | KANDUKUR | KANIGIRI | KANIGIRI |  | 0838026 - MPPS,C.S.PURAM(SC) | PS | Rural | 1 | [5 empty] | 1
51 | C.S.PURAM | KANDUKUR | KANIGIRI | KANIGIRI |  | 0838028 - MPPS,RAMAPURAM | PS | Rural | 1 |  |  |  |  | 1
52 | C.S.PURAM | KANDUKUR | KANIGIRI | KANIGIRI |  | 0838038 - MPPS,NALLAMADUGULA | PS | Rural | 1 | [6 empty] | 1
53 | C.S.PURAM | KANDUKUR | KANIGIRI | KANIGIRI |  | 0838044 - MPPS,VATLA BAYALU | PS | Rural | 2 |  |  |  | 2
54 | C.S.PURAM | KANDUKUR | KANIGIRI | KANIGIRI |  | 0838062 - MPPS,C.S.PURAM(ST) | PS | Rural | 1 | [5 empty] | 1
55 | C.S.PURAM | KANDUKUR | KANIGIRI | KANIGIRI |  | 0838306 - MPUPS,CH.N PALLE | UPS | Rural | 1 | [6 empty] | 1
56 | C.S.PURAM | KANDUKUR | KANIGIRI | KANIGIRI |  | 0838610 - ZPHS,ARIVEMULA | HS | Rural | 1 | [6 empty] | 1
57 | C.S.PURAM | KANDUKUR | KANIGIRI | KANIGIRI |  | 0838009 - MPPS,VADDEPALEM |  |  | 1 | [7 empty] | 1
58 | C.S.PURAM | KANDUKUR | KANIGIRI | KANIGIRI |  | 0838304 - MPUPS,KOVILAMPADU |  |  | 1 | [7 empty] | 1
| C.S.PURAM | [7 empty] | 12 | 0 | 0 | 1 | 2 | 2 | 2 | 3 | 2 | 0
59 | CHIMAKURTHI | ONGOLE | S.N.PADU | ONGOLE | SK.Nazeer | 0829003 - MPPS RANGASAI PURAM | PS | Urban | 1 |  |  |  | 1
60 | CHIMAKURTHI | ONGOLE | S.N.PADU | ONGOLE | SK.Nazeer | 0829017 - MPPS DEVARAPALEM | PS | Urban | 2 | [7 empty] | 2 |  |  |  |  | No Site
61 | CHIMAKURTHI | ONGOLE | S.N.PADU | ONGOLE | SK.Nazeer | 0829027 - MPPS CHIMAKURTHI(N.S.C) | PS | Urban | 1 | [7 empty] | 1 |  |  |  |  | No Site
62 | CHIMAKURTHI | ONGOLE | S.N.PADU | ONGOLE | SK.Nazeer | 0829028 - MPPS YANADI COLONY | PS | Urban | 1 |  |  |  |  | 1
63 | CHIMAKURTHI | ONGOLE | S.N.PADU | ONGOLE | SK.Nazeer | 0829029 - MPPS AMBEDKAR NAGAR | PS | Urban | 2 | [6 empty] | 2
64 | CHIMAKURTHI | ONGOLE | S.N.PADU | ONGOLE | SK.Nazeer | 0829033 MPPS MANCHIKALA PADU(HW) | PS | Urban | 1 |  |  | 1
65 | CHIMAKURTHI | ONGOLE | S.N.PADU | ONGOLE | SK.Nazeer | 0829038 - MPPS GUDIPUDIVARI PALEM | PS | Urban | 1 | [6 empty] | 1
66 | CHIMAKURTHI | ONGOLE | S.N.PADU | ONGOLE | SK.Nazeer | 0829040 - MPPS YELURIVARI PALEM(HW) | PS | Urban | 1 | [6 empty] | 1
67 | CHIMAKURTHI | ONGOLE | S.N.PADU | ONGOLE | SK.Nazeer | 0829042 - MPPS MARRIPALEM | PS | Urban | 1 |  |  |  | 1
68 | CHIMAKURTHI | ONGOLE | S.N.PADU | ONGOLE | SK.Nazeer | 0829045 - MPPS, R.L.PURAM | PS | Urban | 1 | [6 empty] | 1
69 | CHIMAKURTHI | ONGOLE | S.N.PADU | ONGOLE | SK.Nazeer | 0829046 - MPPS RAJUPALEM | PS | Urban | 2 |  |  |  | 2
70 | CHIMAKURTHI | ONGOLE | S.N.PADU | ONGOLE | SK.Nazeer | 0829050 - MPPS G.L.PURAM | PS | Urban | 1 |  |  |  |  | 1
71 | CHIMAKURTHI | ONGOLE | S.N.PADU | ONGOLE | SK.Nazeer | 0829301 - MPUPS ILAPAVULUR | UPS | Urban | 1 |  |  |  |  | 1
72 | CHIMAKURTHI | ONGOLE | S.N.PADU | ONGOLE | SK.Nazeer | 0829015 - MPPS P.NAYUDUPALEM | PS | 1 | 1 | [7 empty] | 1 |  |  |  |  | No Site
73 | CHIMAKURTHI | ONGOLE | S.N.PADU | ONGOLE | SK.Nazeer | 0829302 - MPUPS CHANDRAPADU | UPS | 1 | 1 | [6 empty] | 1
74 | CHIMAKURTHI | ONGOLE | S.N.PADU | ONGOLE |  | 0829036 - MPPS K AGRAHARAM |  |  | 1 | [7 empty] | 1
75 | CHIMAKURTHI | ONGOLE | S.N.PADU | ONGOLE |  | 0829603 - ZPHS BANDLAMUDI |  |  | 2 | [7 empty] | 2
| CHIMAKURTHI | [7 empty] | 21 | 0 | 0 | 1 | 4 | 3 | 0 | 6 | 7 | 0
76 | CHINAGANJAM | ONGOLE | PARCHUR | PARCHUR |  | 0846002 - MPPS,SANTHARAVUR (W) | PS | Rural | 1 | 5.3 |  | 1
77 | CHINAGANJAM | ONGOLE | PARCHUR | PARCHUR |  | 0846019 -MPPS,AMEEN NAGAR | PS | Rural | 1 | 5.3 | [6 empty] | 1 |  |  |  |  | Site Dispute informed to MDO
78 | CHINAGANJAM | ONGOLE | PARCHUR | PARCHUR |  | 0846007 - MPPS,KADAVAKUDURU |  |  | 2 | [7 empty] | 2
79 | CHINAGANJAM | ONGOLE | PARCHUR | PARCHUR |  | 0846603 - ZPHS,PEDAGANJAM |  |  | 1 |  |  | 1 | [9 empty] | Old building to be Dismantling
| CHINAGANJAM | [7 empty] | 5 | 10.6 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0
80 | CHIRALA | ONGOLE | CHIRALA | PARCHUR |  | 0823018 - MPPS THOTAVARIPALEM | PS | Urban | 1 | 5.3 |  | 1
81 | CHIRALA | ONGOLE | CHIRALA | PARCHUR |  | 0823020 - MPPS N.T.R. NAGAR | PS | Urban | 1 | 5.3 |  | 1 | [9 empty] | Amount Not Released
82 | CHIRALA | ONGOLE | CHIRALA | PARCHUR |  | 0823032 - MPPS BEARPET | PS | Urban | 2 | 10.6 | [6 empty] | 2 |  |  |  |  | NO Site
83 | CHIRALA | ONGOLE | CHIRALA | PARCHUR |  | 0823036 - MPPS REDDY PALEM | PS | Urban | 1 | 5.3 |  |  |  | 1
84 | CHIRALA | ONGOLE | CHIRALA | PARCHUR |  | 0823039 - MPPS SEETHANAGAR | PS | Urban | 1 | 5.3 | [5 empty] | 1
85 | CHIRALA | ONGOLE | CHIRALA | PARCHUR |  | 0823043 - MPPS PULLAYAPALEM | PS | Urban | 1 | 5.3 |  |  |  | 1
86 | CHIRALA | ONGOLE | CHIRALA | PARCHUR |  | 0823085 - G V V K S 1ST WARD | PS | Urban | 2 | 10.6 | [6 empty] | 2 |  |  |  |  | No Site
87 | CHIRALA | ONGOLE | CHIRALA | PARCHUR |  | 0823086 - GOVT PS (TW) 1ST WARD | PS | Urban | 1 | 5.3 |  | 1
88 | CHIRALA | ONGOLE | CHIRALA | PARCHUR |  | 0823302 - MPUPS GAVINIVARI PALEM | UPS | Urban | 1 | 5.3 |  |  |  | 1
| CHIRALA | [7 empty] | 11 | 58.3 | 0 | 3 | 0 | 3 | 0 | 1 | 4 | 0
89 | CUMBUM | MARKAPUR | GIDDALUR | KANIGIRI |  | 0834023 - MPPS,PEDANALLA KALVA | PS | Rural | 1 | [5 empty] | 1
90 | CUMBUM | MARKAPUR | GIDDALUR | KANIGIRI |  | 0834026 - MPPS,NARAVAKINDI PALLI | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | Not Required(No strength)
| CUMBUM | [7 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0
91 | DARSI | KANDUKUR | DARSI | ADDANKI | SK.Mastanvali | 0813022 - MPPS DARSI (N S C COLONY) | PS | Rural | 2 | [6 empty] | 2 |  |  | 2 | 0
92 | DARSI | KANDUKUR | DARSI | ADDANKI | SK.Mastanvali | 0813040 - MPPS EAST VERAY PALEM SC | PS | Rural | 1 |  |  |  | 1 | [5 empty] | 1 | 0
93 | DARSI | KANDUKUR | DARSI | ADDANKI | SK.Mastanvali | 0813046 - MPPS BOTLAPALEM SC | PS | Rural | 1 |  | 1 | [7 empty] | 1 | 0 |  | Due to not Deposition of amount in favour of SMC the work could not be taken up
94 | DARSI | KANDUKUR | DARSI | ADDANKI | SK.Mastanvali | 0813050 - MPPS JAMUKULADINNE | PS | Rural | 1 | [7 empty] | 1 |  | 1 | 0 |  | Not Requied
95 | DARSI | KANDUKUR | DARSI | ADDANKI | SK.Mastanvali | 0813057 - MPPS PEDA VUYYALAWADA | PS | Rural | 2 | [6 empty] | 2 |  |  | 2 | 0
96 | DARSI | KANDUKUR | DARSI | ADDANKI | SK.Mastanvali | 0813065 - GVVKS DARSI | PS | Rural | 1 | [6 empty] | 1 |  |  | 1 | 0
97 | DARSI | KANDUKUR | DARSI | ADDANKI | SK.Mastanvali | 0813067-MPPS EAST VENKATA PURAM SC | PS | Rural | 1 |  |  | 1 | [6 empty] | 1 | 0
98 | DARSI | KANDUKUR | DARSI | ADDANKI | SK.Mastanvali | 0813068 - MPPS LURDH GIRI COLONY | PS | Rural | 1 | [6 empty] | 1 |  |  | 1 | 0
99 | DARSI | KANDUKUR | DARSI | ADDANKI | SK.Mastanvali | 0813070 - MPPS EAST VENKATA PURAM | PS | Rural | 2 |  |  | 2 | [6 empty] | 2 | 0
100 | DARSI | KANDUKUR | DARSI | ADDANKI | SK.Mastanvali | 0813302 - MPUPS SHESAMVARIPALEM | UPS | Rural | 2 |  |  | 2 | [6 empty] | 2 | 0
101 | DARSI | KANDUKUR | DARSI | ADDANKI | SK.Mastanvali | 0813312 - MPUPS EAST VEERAYA PALEM | UPS | Rural | 1 |  |  | 1 | [6 empty] | 1 | 0
102 | DARSI | KANDUKUR | DARSI | ADDANKI |  | 0813039 - MPPS EAST CHOUTAPALEM SC |  |  | 1 | [7 empty] | 1
103 | DARSI | KANDUKUR | DARSI | ADDANKI |  | 0813043 - MPPS POTHA KAMURU |  |  | 1 | [7 empty] | 1
104 | DARSI | KANDUKUR | DARSI | ADDANKI |  | 0813049 - MPPS SAMANTHAPUDI |  |  | 3 | [7 empty] | 3
| DARSI | [7 empty] | 20 | 0 | 1 | 6 | 1 | 0 | 0 | 6 | 6 | 0
105 | DONAKONDA | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0805001 - MPPS BATTEPADU | PS | Rural | 1 |  | 1 | [7 empty] | 1 | 0
106 | DONAKONDA | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0805009 - MPPS W.LAKSHMI PURAM SC | PS | Rural | 1 |  |  | 1 | [6 empty] | 1 | 0
107 | DONAKONDA | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0805016 - MPPS BADA PURAM (GEN) | PS | Rural | 1 |  | 1 | [7 empty] | 1 | 0
108 | DONAKONDA | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0805022 - MPPS YERRA BALEM GEN | PS | Rural | 1 | [7 empty] | 1 |  | 1 | 0 |  | No site
109 | DONAKONDA | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0805029 - MPPS RAGAMAKKA PALLI | PS | Rural | 1 | [7 empty] | 1 |  | 1 | 0
110 | DONAKONDA | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0805035 - MPPS MALLAM PETA (SC) | PS | Rural | 1 | [7 empty] | 1 |  | 1 | 0
111 | DONAKONDA | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0805037 - MPPS KATTAKINDI PALLI | PS | Rural | 1 |  | 1 | [7 empty] | 1 | 0
112 | DONAKONDA | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0805041 - MPPS ANANTHAVARAM | PS | Rural | 2 |  |  |  | 2 | [5 empty] | 2 | 0
113 | DONAKONDA | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0805044 - MPPS MANGINAPUDI (SC) | PS | Rural | 1 |  |  | 1 | [6 empty] | 1 | 0
114 | DONAKONDA | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0805050 - MPPS PEDA GUDIPADU (SC) | PS | Rural | 1 |  |  | 1 | [6 empty] | 1 | 0
115 | DONAKONDA | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0805059 - MPPS SANGAPURAM AA | PS | Rural | 1 | [7 empty] | 1 |  | 1 | 0 |  | Not Requied
116 | DONAKONDA | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0805074-MPPS GANGADEVAPALLI | PS | Rural | 2 |  |  | 1 |  |  | 1 |  |  |  | 2 | 0
117 | DONAKONDA | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0805075 - MPPS MANGINAPUDI | PS | Rural | 2 |  |  |  | 2 | [5 empty] | 2 | 0
118 | DONAKONDA | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0805301 - MPUPS INDLA CHERUVU | UPS | Rural | 1 | [6 empty] | 1 |  |  | 1 | 0
119 | DONAKONDA | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0805307 - MPUPS POLE PALLI | UPS | Rural | 2 |  |  | 2 | [6 empty] | 2 | 0
120 | DONAKONDA | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0805607-ZPHS GANGADEVAPALLI | HS | Rural | 1 |  |  | 1 | [6 empty] | 1 | 0
121 | DONAKONDA | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0805017 - MPPS BADA PURAM (SC) | PS | Rural | 1 |  |  | 1 | [6 empty] | 1 | 0
122 | DONAKONDA | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0805003 - MPPS DESIREDDY PALLI | PS | 1 | 1 |  |  |  | 1 | [5 empty] | 1 | 0
123 | DONAKONDA | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0805074-MPPS GANGADEVAPALLI | PS | 1 | 1 |  |  |  |  | 1 |  |  |  |  | 1 | 0
| DONAKONDA | [7 empty] | 23 | 0 | 3 | 8 | 5 | 1 | 1 | 1 | 4 | 0
124 | GIDDALURU | MARKAPUR | GIDDALUR | KANIGIRI |  | 0836009 - MPPS,KRISHNAMRAJU PALLI | PS | Urban | 1 |  |  |  |  | 1
125 | GIDDALURU | MARKAPUR | GIDDALUR | KANIGIRI |  | 0836012 - MPPS,KONGALA VEEDU | PS | Urban | 1 | [5 empty] | 1
126 | GIDDALURU | MARKAPUR | GIDDALUR | KANIGIRI |  | 0836019 - MPPS S.B.TEMPLE,GIDDALUR | PS | Urban | 1 | [5 empty] | 1
127 | GIDDALURU | MARKAPUR | GIDDALUR | KANIGIRI |  | 0836023 - MPPS,MITTAMEDIPALLI | PS | Urban | 1 | [7 empty] | 1 |  |  |  |  | No Site
128 | GIDDALURU | MARKAPUR | GIDDALUR | KANIGIRI |  | 0836026 - MPPS,UPPALAPADU | PS | Urban | 1 | [6 empty] | 1
129 | GIDDALURU | MARKAPUR | GIDDALUR | KANIGIRI |  | 0836040 - MPPS,MUNDLA PADU MAIN | PS | Urban | 1 |  |  | 1
130 | GIDDALURU | MARKAPUR | GIDDALUR | KANIGIRI |  | 0836046 - MPPS,SANJEEVARAO PETA | PS | Urban | 1 | [6 empty] | 1
131 | GIDDALURU | MARKAPUR | GIDDALUR | KANIGIRI |  | 0836051 - MPPS,DANTHARA PALLI | PS | Urban | 1 |  |  | 1
132 | GIDDALURU | MARKAPUR | GIDDALUR | KANIGIRI |  | 0836302 - MPUPS,NARAVABOYANA PALLI | UPS | Urban | 2 | [6 empty] | 2
133 | GIDDALURU | MARKAPUR | GIDDALUR | KANIGIRI |  | 0836012 - MPPS,KONGALA VEEDU | PS | 1 | 1 |  |  |  |  | 1
134 | GIDDALURU | MARKAPUR | GIDDALUR | KANIGIRI |  | 0836019 - MPPS S.B.TEMPLE,GIDDALUR | PS | 1 | 1 | [5 empty] | 1
135 | GIDDALURU | MARKAPUR | GIDDALUR | KANIGIRI |  | 0836603 - ZPHS (G), GIDDALUR (PT) |  |  | 2 |  |  | 2
136 | GIDDALURU | MARKAPUR | GIDDALUR | KANIGIRI |  | 0836604 - ZPHS,K.S.PALLI |  |  | 4 | [7 empty] | 4
| GIDDALURU | [7 empty] | 18 | 0 | 0 | 4 | 0 | 2 | 3 | 4 | 5 | 0 | 0 | 0 | 0
137 | GUDLURU | KANDUKUR | KANDUKUR | KANDUKUR | Venkateswara Rao | 0854011 - MPPS,VENKATESWARAPURAM | PS | Rural | 1 |  |  | 1
138 | GUDLURU | KANDUKUR | KANDUKUR | KANDUKUR | Venkateswara Rao | 0854020 - MPPS,CHENCHIREDDY PALEM | PS | Rural | 1 | [6 empty] | 1
139 | GUDLURU | KANDUKUR | KANDUKUR | KANDUKUR | Venkateswara Rao | 0854023 - MPPS,PURETIPALLI | PS | Rural | 1 | [6 empty] | 1
140 | GUDLURU | KANDUKUR | KANDUKUR | KANDUKUR | Venkateswara Rao | 0854039 - MPPS,TETTU WEST | PS | Rural | 1 |  | 1 | [11 empty] | 0
141 | GUDLURU | KANDUKUR | KANDUKUR | KANDUKUR | Venkateswara Rao | 0854309 - MPUPS,ELERUPADU | UPS | Rural | 1 |  |  | 1
142 | GUDLURU | KANDUKUR | KANDUKUR | KANDUKUR | Venkateswara Rao | 0854312 - MPUPS,ADAVIRAJU PALEM | UPS | Rural | 1 | [7 empty] | 1
143 | GUDLURU | KANDUKUR | KANDUKUR | KANDUKUR | Venkateswara Rao | 0854315 - MPUPS,PARAKONDAPADU | UPS | Rural | 2 |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 1 ACR Not requied
144 | GUDLURU | KANDUKUR | KANDUKUR | KANDUKUR | Venkateswara Rao | 0854024 - MPPS,VENKAMPETA | PS | Rural | 1 |  |  | 1
145 | GUDLURU | KANDUKUR | KANDUKUR | KANDUKUR | Venkateswara Rao | 0854028 - MPPS,R.C.AGRAHARAM | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | Not Requied
146 | GUDLURU | KANDUKUR | KANDUKUR | KANDUKUR | Venkateswara Rao | 0854045 - MPPS,M. PATTAPUPALEM | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | Not Requied
147 | GUDLURU | KANDUKUR | KANDUKUR | KANDUKUR |  | 0854052-MPPSBASIREDDYPALEM |  |  | 1 | [7 empty] | 1
148 | GUDLURU | KANDUKUR | KANDUKUR | KANDUKUR |  | 0854053-MPPS,CHINALATRAPI |  |  | 1 | [7 empty] | 1
149 | GUDLURU | KANDUKUR | KANDUKUR | KANDUKUR |  | 0854305 - MPUPS,NAYUDUPALEM |  |  | 1 | [7 empty] | 1
150 | GUDLURU | KANDUKUR | KANDUKUR | KANDUKUR |  | 0854306 - MPUPS,POTLURU |  |  | 1 | [7 empty] | 1
151 | GUDLURU | KANDUKUR | KANDUKUR | KANDUKUR |  | 0854315 - MPUPS,PARAKONDAPADU |  |  | 2 | [7 empty] | 2
152 | GUDLURU | KANDUKUR | KANDUKUR | KANDUKUR |  | 0854605-ZPHS,CHEVURU |  |  | 1 | [7 empty] | 1
| GUDLURU | [7 empty] | 18 | 0 | 1 | 4 | 0 | 0 | 0 | 2 | 11 | 0
153 | H.M.PADU | KANDUKUR | KANIGIRI | KANIGIRI |  | 0832017 - MPPS,VEMULA PADU(DPEP) | PS | Rural | 1 | [6 empty] | 1
154 | H.M.PADU | KANDUKUR | KANIGIRI | KANIGIRI |  | 0832034 - MPPS, GAYAMVARIPALLI | PS | Rural | 1 |  | 1
155 | H.M.PADU | KANDUKUR | KANIGIRI | KANIGIRI |  | 0832037 - MPPS,VALICHERLA CP | PS | Rural | 1 | [5 empty] | 1
156 | H.M.PADU | KANDUKUR | KANIGIRI | KANIGIRI |  | 0832039 - MPPS,VEERARAMA PURAM | PS | Rural | 2 |  |  |  | 2
157 | H.M.PADU | KANDUKUR | KANIGIRI | KANIGIRI |  | 0832042-MPPS,MUPPALLA PADU JN | PS | Rural | 1 |  |  | 1
158 | H.M.PADU | KANDUKUR | KANIGIRI | KANIGIRI |  | 0832060 - MPPS, K.S.PURAM | PS | Rural | 1 | [6 empty] | 1
159 | H.M.PADU | KANDUKUR | KANIGIRI | KANIGIRI |  | 0832309 - MPUPS,DASARIPALLI | UPS | Rural | 1 | [6 empty] | 1
160 | H.M.PADU | KANDUKUR | KANIGIRI | KANIGIRI |  | 0832001 - MPPS,THALLAVARIPALLI | PS | Rural | 1 | [6 empty] | 1
161 | H.M.PADU | KANDUKUR | KANIGIRI | KANIGIRI |  | 0832005 - MPPS,CHINNA UMMANAPALLI | PS | Rural | 1 |  | 1
162 | H.M.PADU | KANDUKUR | KANIGIRI | KANIGIRI |  | 0832020 - MPPS,THIMMAREDDI PALLI | PS | Rural | 1 | [6 empty] | 1
163 | H.M.PADU | KANDUKUR | KANIGIRI | KANIGIRI |  | 0832053 - MPPS,KISTAMPALLI | PS | Rural | 1 | [6 empty] | 1
164 | H.M.PADU | KANDUKUR | KANIGIRI | KANIGIRI |  | 0832062 - MPPS,KANCHARLAPALEM | PS | Rural | 1 | [5 empty] | 1
165 | H.M.PADU | KANDUKUR | KANIGIRI | KANIGIRI |  | 0832602 - ZPHS,PEDAGOLLA PALLI |  |  | 1 | [7 empty] | 1
166 | H.M.PADU | KANDUKUR | KANIGIRI | KANIGIRI |  | 0832604 - ZPHS,MUPPALLA PADU |  |  | 2 | [7 empty] | 2
| H.M.PADU | [7 empty] | 16 | 0 | 2 | 1 | 2 | 0 | 2 | 6 | 3 | 0
167 | INKOLLU | ONGOLE | PARCHUR | PARCHUR |  | 0825003 - MPPS IDUPULAPADU NORTH | PS | Rural | 1 | 5.3 | [5 empty] | 1
168 | INKOLLU | ONGOLE | PARCHUR | PARCHUR |  | 0825005 - MPPS IDUPULAPADU | PS | Rural | 1 | 5.3 | [5 empty] | 1
169 | INKOLLU | ONGOLE | PARCHUR | PARCHUR |  | 0825032 - MPPS NALATHAOTIVARIPALEM | PS | Rural | 1 | 5.3 |  |  |  | 1
170 | INKOLLU | ONGOLE | PARCHUR | PARCHUR |  | 0825303 - MPUPS GOLLAPALEM | UPS | Rural | 2 | 10.6 | [5 empty] | 2
171 | INKOLLU | ONGOLE | PARCHUR | PARCHUR |  | 0825009 - MPPS PUSAPADU (LE) | PS | Rural | 1 | 5.3 |  |  |  | 1
172 | INKOLLU | ONGOLE | PARCHUR | PARCHUR |  | 0825004 - MPPS IDUPULAPADU CHURCH R |  |  | 1 |  |  | 1
| INKOLLU | [7 empty] | 7 | 31.8 | 0 | 1 | 0 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 0
31 | J.PANGULUR | ONGOLE | ADDANKI | ADDANKI | P.Subba Rao | 0826004 - MPPS KONDAMANJULUR MAIN | PS | Rural | 1 |  | 1 | [7 empty] | 1 | 0
32 | J.PANGULUR | ONGOLE | ADDANKI | ADDANKI | P.Subba Rao | 0826008 - MPPS KALLAMVARIPALEM | PS | Rural | 1 | [7 empty] | 1 |  | 1 | 0
33 | J.PANGULUR | ONGOLE | ADDANKI | ADDANKI | P.Subba Rao | 0826017 - MPPS J.PANGULURU | PS | Rural | 1 | [6 empty] | 1 |  |  | 1 | 0
34 | J.PANGULUR | ONGOLE | ADDANKI | ADDANKI | P.Subba Rao | 0826019 - MPPS J.PANGULURU ST | PS | Rural | 1 |  |  |  | 1 | [5 empty] | 1 | 0
35 | J.PANGULUR | ONGOLE | ADDANKI | ADDANKI | P.Subba Rao | 0826306 - MPUPS 31 T.KOPPERA PADU | UPS | Rural | 1 |  |  | 1 | [6 empty] | 1 | 0
36 | J.PANGULUR | ONGOLE | ADDANKI | ADDANKI | P.Subba Rao | 0826014 - MPPS BUDAWADA MAIN | PS | 1 | 1 |  | 1 | [7 empty] | 1 | 0
37 | J.PANGULUR | ONGOLE | ADDANKI | ADDANKI |  | 0826304 - MPUPS RENINGAVARAM |  |  | 1 | [7 empty] | 1
| J.PANGULUR | [7 empty] | 7 | 0 | 2 | 1 | 1 | 0 | 0 | 1 | 2 | 0
180 | K.K.MITLA | KANDUKUR | MARKAPUR | ONGOLE |  | 0811001 - MPPS GANIVANI PADU | PS | Rural | 1 | [6 empty] | 1
181 | K.K.MITLA | KANDUKUR | MARKAPUR | ONGOLE |  | 0811004 - MPPS UMMAYAPALEM | PS | Rural | 1 | [6 empty] | 1
182 | K.K.MITLA | KANDUKUR | MARKAPUR | ONGOLE |  | 0811008 - MPPS ADIANDHRA COLONY | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | No Site
183 | K.K.MITLA | KANDUKUR | MARKAPUR | ONGOLE |  | 0811013 - MPPS ADIANDHRA COLONY | PS | Rural | 2 | [7 empty] | 2 |  |  |  |  | No Site
184 | K.K.MITLA | KANDUKUR | MARKAPUR | ONGOLE |  | 0811016 - MPPS AMBAPURAM(AA) | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | Not Requied
185 | K.K.MITLA | KANDUKUR | MARKAPUR | ONGOLE |  | 0811018 - MPPS GURRALAMADUGU | PS | Rural | 1 |  |  | 1 | [9 empty] | Work stopped due to political dispute
186 | K.K.MITLA | KANDUKUR | MARKAPUR | ONGOLE |  | 0811025 - MPPS ADIANDHRA CLY. | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | Not Requied
187 | K.K.MITLA | KANDUKUR | MARKAPUR | ONGOLE |  | 0811027 - MPPS EDURALLA PADU (H) | PS | Rural | 1 | [6 empty] | 1
188 | K.K.MITLA | KANDUKUR | MARKAPUR | ONGOLE |  | 0811034 - MPPS SIDDAVARAM AA | PS | Rural | 1 | [6 empty] | 1
189 | K.K.MITLA | KANDUKUR | MARKAPUR | ONGOLE |  | 0811040 - MPPS OBULAREDDIPALLI | PS | Rural | 1 | [6 empty] | 1
190 | K.K.MITLA | KANDUKUR | MARKAPUR | ONGOLE |  | 0811062 - MPPS NAIDUPETA (HINDU) | PS | Rural | 1 | [5 empty] | 1
191 | K.K.MITLA | KANDUKUR | MARKAPUR | ONGOLE |  | 0811063 - MPPS NAIDUPETA AA | PS | Rural | 1 | [5 empty] | 1
192 | K.K.MITLA | KANDUKUR | MARKAPUR | ONGOLE |  | 0811068 - MPPS YEDUBOTIVARI PALLI | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | Site dispute
193 | K.K.MITLA | KANDUKUR | MARKAPUR | ONGOLE |  | 0811087 - MPPS MARRIPALEM | PS | Rural | 1 | [6 empty] | 1
194 | K.K.MITLA | KANDUKUR | MARKAPUR | ONGOLE |  | 0811303 - MPUPS NAGARAJU GUNTA | UPS | Rural | 1 | [6 empty] | 1
195 | K.K.MITLA | KANDUKUR | MARKAPUR | ONGOLE |  | 0811306 - MPUPS NAGAMPALLI | UPS | Rural | 4 | [7 empty] | 4 |  |  |  |  | 3 not required 1 local dispute
196 | K.K.MITLA | KANDUKUR | MARKAPUR | ONGOLE |  | 0811605 - APSWRS JRC VELUGONDA | HSS | Rural | 3 |  |  |  |  | 1 |  | 2
197 | K.K.MITLA | KANDUKUR | MARKAPUR | ONGOLE |  | 0811035 - MPPS CHERLOPALLI | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | Not Requied
198 | K.K.MITLA | KANDUKUR | MARKAPUR | ONGOLE |  | 0811049 - MPPS CHOUTAPALLI SC | PS | Rural | 1 | [6 empty] | 1
199 | K.K.MITLA | KANDUKUR | MARKAPUR | ONGOLE |  | 0811086 - MPPS NAGIREDDYPALLI | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | Not Requied
| K.K.MITLA | [7 empty] | 26 | 0 | 0 | 1 | 0 | 1 | 2 | 10 | 12 | 0 | 0 | 0 | 0
200 | KANDUKUR | KANDUKUR | KANDUKUR | KANDUKUR | K.Srinivasa Rao | 0850021 - MPPS,GUTHI KONDAVARI PALEM | PS | Urban | 1 | [7 empty] | 1 |  |  |  |  | Dismantling
201 | KANDUKUR | KANDUKUR | KANDUKUR | KANDUKUR | K.Srinivasa Rao | 0850032 - MPPS,OGURU (AAC) | PS | Urban | 1 |  |  | 1
202 | KANDUKUR | KANDUKUR | KANDUKUR | KANDUKUR | K.Srinivasa Rao | 0850035 - MPPS (URDU,KHAJIPALEM) | PS | Urban | 1 | [6 empty] | 1
203 | KANDUKUR | KANDUKUR | KANDUKUR | KANDUKUR | K.Srinivasa Rao | 0850039 - MPPS,GOKARAJUVARI STREET | PS | Urban | 1 | [7 empty] | 1 |  |  |  |  | Site problem
204 | KANDUKUR | KANDUKUR | KANDUKUR | KANDUKUR | K.Srinivasa Rao | 0850053 - MPPS, 1W JANARDHANA CLY | PS | Urban | 1 |  |  |  | 1
205 | KANDUKUR | KANDUKUR | KANDUKUR | KANDUKUR | K.Srinivasa Rao | 0850057 - MPPS,SANTHOSH NAGAR | PS | Urban | 2 |  |  | 2
206 | KANDUKUR | KANDUKUR | KANDUKUR | KANDUKUR | K.Srinivasa Rao | 0850058 - MPPS,24th WARD M NAGAR. | PS | Urban | 2 | [6 empty] | 2
207 | KANDUKUR | KANDUKUR | KANDUKUR | KANDUKUR | K.Srinivasa Rao | 0850070 - MPPS,MOPADU | PS | Urban | 1 |  |  | 1
208 | KANDUKUR | KANDUKUR | KANDUKUR | KANDUKUR | K.Srinivasa Rao | 0850072 - MPPS,MACHAVARAM(HP) | PS | Urban | 1 | [7 empty] | 1 |  |  |  |  | Dismantling
209 | KANDUKUR | KANDUKUR | KANDUKUR | KANDUKUR | K.Srinivasa Rao | 0850078 - MPPS,PALUR (HP) | PS | Urban | 1 |  |  |  | 1
210 | KANDUKUR | KANDUKUR | KANDUKUR | KANDUKUR | K.Srinivasa Rao | 0850303 - MPUPS,ALLAMVARI PALEM | UPS | Urban | 1 |  | 1
211 | KANDUKUR | KANDUKUR | KANDUKUR | KANDUKUR | K.Srinivasa Rao | 0850306 - MPUPS,MOPADU | UPS | Urban | 1 | [6 empty] | 1
212 | KANDUKUR | KANDUKUR | KANDUKUR | KANDUKUR | K.Srinivasa Rao | 0850307 - MPUPS,PALURU | UPS | Urban | 2 |  |  |  | 2
213 | KANDUKUR | KANDUKUR | KANDUKUR | KANDUKUR | K.Srinivasa Rao | 0850311-MPUPS,MAHADEVAPURAM | UPS | Urban | 1 |  |  |  | 1
214 | KANDUKUR | KANDUKUR | KANDUKUR | KANDUKUR | K.Srinivasa Rao | 0850007 - MPPS,BALIJAPALEM(GEN) | PS | Urban | 1 |  | 1
215 | KANDUKUR | KANDUKUR | KANDUKUR | KANDUKUR |  | 0850301 - MPUPS,VIKKIRALAPETA |  |  | 1 | [7 empty] | 1
| KANDUKUR | [7 empty] | 19 | 0 | 2 | 4 | 5 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0
216 | KANIGIRI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0831001 - MPPS GANUGAPENTA | PS | Urban | 1 |  |  |  | 1
217 | KANIGIRI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0831003 - MPPS PATTABHIRAMA PURAM | PS | Urban | 2 |  |  | 2
218 | KANIGIRI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0831020 - MPPS KNG 4TH WARD | PS | Urban | 1 | [5 empty] | 1
219 | KANIGIRI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0831023 - MPPS KNG 8TH WARD | PS | Urban | 2 | [7 empty] | 2 |  |  |  |  | No Site
220 | KANIGIRI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0831024 - MPPS KANIGIRI PATHURU | PS | Urban | 1 | [5 empty] | 1
221 | KANIGIRI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0831025 - MPPS KANIGIRI(D.STREET) | PS | Urban | 1 |  |  | 1
222 | KANIGIRI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0831033 - MPPS CHAKIRALA HP | PS | Urban | 1 | [5 empty] | 1
223 | KANIGIRI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0831042 - MPPS CHINTHALAPALEM HP | PS | Urban | 1 | [5 empty] | 1
224 | KANIGIRI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0831046 - MPPS BIJJAMVARI PALLI | PS | Urban | 1 |  |  |  |  | 1
225 | KANIGIRI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0831052-MPPS KOTHAPALEM OF GUDIPADU | PS | Urban | 1 | [7 empty] | 1 |  |  |  |  | DISMANTLING (refered to P.R.Department)
226 | KANIGIRI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0831056 - MPPS AZEES PURAM | PS | Urban | 1 | [5 empty] | 1
227 | KANIGIRI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0831069 - MPPS KOTHAPALLI | PS | Urban | 1 | [6 empty] | 1
228 | KANIGIRI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0831071 - MPPS JAMMALAMADAKA | PS | Urban | 2 | [6 empty] | 2
229 | KANIGIRI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0831074 - MPPS EGUVAPALLI | PS | Urban | 1 | [7 empty] | 1 |  |  |  |  | Dismantling
230 | KANIGIRI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0831088 - MPPS USTHUMVARI PALLI | PS | Urban | 1 | [6 empty] | 1
231 | KANIGIRI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0831301 - MPUPS BADUGULERU | UPS | Urban | 1 |  |  |  |  | 1
232 | KANIGIRI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0831313 - MPUPS CHEERLA DINNE | UPS | Urban | 1 | [7 empty] | 1 |  |  |  |  | Dismantling
233 | KANIGIRI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0831319 - MPUPS KALAGATLA | UPS | Urban | 1 | [6 empty] | 1
234 | KANIGIRI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0831328- MPUPS YADAVALLI | UPS | Urban | 2 | [6 empty] | 2
235 | KANIGIRI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0831037 - MPPS TURAKA PALLI | PS | Urban | 1 | [5 empty] | 1
236 | KANIGIRI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0831051 - MPPS GOVINDUVARI PALEM | PS | Urban | 1 | [5 empty] | 1
237 | KANIGIRI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0831313 - MPUPS CHEERLA DINNE | UPS | Urban | 1 | [6 empty] | 1
238 | KANIGIRI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0831015 - MPPS MUKKUKASIREDDYNAGAR | PS | 1 | 1 |  |  | 1
239 | KANIGIRI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0831616-ZPHS PATHAPADU |  |  | 2 | [7 empty] | 2
| KANIGIRI | [7 empty] | 29 | 0 | 0 | 4 | 1 | 2 | 7 | 8 | 7 | 0 | 0 | 0 | 0
240 | KARAMCHEDU | ONGOLE | PARCHUR | PARCHUR |  | 0822015 - MPPS THIMIDITAPADU | PS | Rural | 1 | 5.3 |  | 1
241 | KARAMCHEDU | ONGOLE | PARCHUR | PARCHUR |  | 0822303 - MPUPS KARAMCHEDU | UPS | Rural | 1 | 5.3 | [6 empty] | 1
242 | KARAMCHEDU | ONGOLE | PARCHUR | PARCHUR |  | 0822006 - MPPS KARAMCHEDU PP | PS | Rural | 1 | 5.3 |  | 1
243 | KARAMCHEDU | ONGOLE | PARCHUR | PARCHUR |  | 0822018 - MPPS DAGGUBADU AB NAGAR |  |  | 1 |  |  | 1
244 | KARAMCHEDU | ONGOLE | PARCHUR | PARCHUR |  | 0822022 - MPPS SWARNA PALEM |  |  | 1 |  |  | 1
| KARAMCHEDU | [7 empty] | 5 | 15.9 | 0 | 4 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
245 | KOMAROLU | MARKAPUR | GIDDALUR | KANIGIRI |  | 0837031 - MPPS,MALIKAPALLI | PS | Rural | 1 |  |  | 1
246 | KOMAROLU | MARKAPUR | GIDDALUR | KANIGIRI |  | 0837032 - MPPS,KASINEPALLI | PS | Rural | 1 |  | 1
247 | KOMAROLU | MARKAPUR | GIDDALUR | KANIGIRI |  | 0837055 - MPPS,ALLINAGARAM | PS | Rural | 1 |  |  | 1
248 | KOMAROLU | MARKAPUR | GIDDALUR | KANIGIRI |  | 0837069-MPPS,POTHIREDDY PALLI BC | PS | Rural | 1 | [6 empty] | 1
249 | KOMAROLU | MARKAPUR | GIDDALUR | KANIGIRI |  | 0837302 - MPUPS,EDAMAKALLU | UPS | Rural | 1 | [6 empty] | 1
250 | KOMAROLU | MARKAPUR | GIDDALUR | KANIGIRI |  | 0837304 - MPUPS,BODDUVANIPALLI | UPS | Rural | 1 |  |  |  | 1
| KOMAROLU | [7 empty] | 6 | 0 | 1 | 2 | 1 | 0 | 0 | 2 | 0 | 0
251 | KONDAPI | KANDUKUR | KONDAPI | KANDUKUR | Venkateswara Rao | 0842002 - MPPS,MUGACHINTALA (AAW) | PS | Rural | 1 | [6 empty] | 1
252 | KONDAPI | KANDUKUR | KONDAPI | KANDUKUR | Venkateswara Rao | 0842022 - MPPS,KUMMARI PALEM | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | Site problem
253 | KONDAPI | KANDUKUR | KONDAPI | KANDUKUR | Venkateswara Rao | 0842025 - MPPS,PERIDEPI (AAP) | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | Not Requied
254 | KONDAPI | KANDUKUR | KONDAPI | KANDUKUR | Venkateswara Rao | 0842036 - MPPS,CHINA VENKANA PALM | PS | Rural | 1 |  |  | 1
255 | KONDAPI | KANDUKUR | KONDAPI | KANDUKUR | Venkateswara Rao | 0842301 - MPUPS,MUGACHINTALA (VILL) | UPS | Rural | 2 |  |  |  | 1 |  |  | 1
256 | KONDAPI | KANDUKUR | KONDAPI | KANDUKUR | Venkateswara Rao | 0842303 - MPUPS,ANAKARLAPUDI (VILL) | UPS | Rural | 1 | [7 empty] | 1 |  |  |  |  | Not Requied
257 | KONDAPI | KANDUKUR | KONDAPI | KANDUKUR | Venkateswara Rao | 0842305 - MPUPS,JARLAPALEM | UPS | Rural | 1 |  |  |  | 1
258 | KONDAPI | KANDUKUR | KONDAPI | KANDUKUR | Venkateswara Rao | 0842009 - MPPS,ANAKARLAPUDI (AAW) | PS | Rural | 1 |  |  |  | 1
259 | KONDAPI | KANDUKUR | KONDAPI | KANDUKUR | Venkateswara Rao | 0842028 - MPPS,MUPPAVARAM SC CLNY | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | No site
260 | KONDAPI | KANDUKUR | KONDAPI | KANDUKUR |  | 0842011 - MPPS,K.G.KANDRIKA (VILL) |  |  | 1 | [7 empty] | 1
261 | KONDAPI | KANDUKUR | KONDAPI | KANDUKUR |  | 0842015 - MPPS,THATAKULAPALEM |  |  | 1 | [7 empty] | 1
262 | KONDAPI | KANDUKUR | KONDAPI | KANDUKUR |  | 0842041 - MPPS,PEDAKANDLAGUNTA |  |  | 2 | [7 empty] | 2
263 | KONDAPI | KANDUKUR | KONDAPI | KANDUKUR |  | 0842602 - ZPHS,NETHIVARIPALEM |  |  | 1 | [7 empty] | 1
| KONDAPI | [7 empty] | 15 | 0 | 0 | 1 | 3 | 0 | 0 | 2 | 9 | 0
38 | KORISAPADU | ONGOLE | ADDANKI | ADDANKI | P.Subba Rao | 0827007 - MPPS THIMMANAPALEM(G) | PS | Rural | 2 |  |  | 2 | [6 empty] | 2 | 0
39 | KORISAPADU | ONGOLE | ADDANKI | ADDANKI | P.Subba Rao | 0827302 - MPUPS BODDUVANI PALEM | UPS | Rural | 1 |  |  |  |  | 1 |  |  |  |  | 1 | 0
| KORISAPADU | [7 empty] | 3 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0
266 | KOTHAPATNAM | ONGOLE | ONGOLE | ONGOLE | J.V.Ramana Murthy | 0847002 - MPPS,ALOOR | PS | Rural | 1 |  |  |  | 1
267 | KOTHAPATNAM | ONGOLE | ONGOLE | ONGOLE | J.V.Ramana Murthy | 0847004 - MPPS-II, PADARTHI | PS | Rural | 1 | [6 empty] | 1
268 | KOTHAPATNAM | ONGOLE | ONGOLE | ONGOLE | J.V.Ramana Murthy | 0847010 - MPPS,KOTHAPATNAM-64 | PS | Rural | 1 | [6 empty] | 1
269 | KOTHAPATNAM | ONGOLE | ONGOLE | ONGOLE | J.V.Ramana Murthy | 0847017 - MPPS,ALLUR ,HARIJANAWADA | PS | Rural | 2 |  |  | 2
270 | KOTHAPATNAM | ONGOLE | ONGOLE | ONGOLE | J.V.Ramana Murthy | 0847018 - MPPS,ALLURU (URDU) | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | Dismantling
271 | KOTHAPATNAM | ONGOLE | ONGOLE | ONGOLE | J.V.Ramana Murthy | 0847020 - MPPS,ALLURU, R.R.COLONY | PS | Rural | 1 |  |  |  | 1
272 | KOTHAPATNAM | ONGOLE | ONGOLE | ONGOLE | J.V.Ramana Murthy | 0847019 - MPPS,ALLURU T.Y. COLONY | PS | Rural | 1 |  |  |  |  | 1
273 | KOTHAPATNAM | ONGOLE | ONGOLE | ONGOLE | J.V.Ramana Murthy | 0847301 - MPUPS,MOTUMALA | UPS | 1 | 1 |  |  |  | 1
274 | KOTHAPATNAM | ONGOLE | ONGOLE | ONGOLE | J.V.Ramana Murthy | 0847602 - ZPHS , KOTHAPATNAM |  |  | 2 | [6 empty] | 2
275 | KOTHAPATNAM | ONGOLE | ONGOLE | ONGOLE |  | 0847007 - MPPS,GUNDAMALA |  |  | 1 | [7 empty] | 1
| KOTHAPATNAM | [7 empty] | 12 | 0 | 0 | 2 | 3 | 1 | 0 | 4 | 2 | 0
276 | KURICHEDU | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0804007 - MPPS WEST NAIDUPALEM (U) | PS | Rural | 1 |  |  | 1 | [6 empty] | 1 | 0
277 | KURICHEDU | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0804021 - MPPS KATAMVARI PALLE | PS | Rural | 1 | [7 empty] | 1 |  | 1 | 0 |  | Dismantling
278 | KURICHEDU | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0804031 - MPPS WEST GANGAVARAM (AA) | PS | Rural | 1 | [6 empty] | 1 |  |  | 1 | 0
279 | KURICHEDU | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0804046 - GOVT PS RAMANJANEYA COLNY | PS | Rural | 1 | [7 empty] | 1 |  | 1 | 0 |  | Not Requied
280 | KURICHEDU | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0804048 - MPPS KALLUR | PS | Rural | 1 | [7 empty] | 1 |  | 1 | 0
281 | KURICHEDU | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0804305-MPUPS AGRAHARAM (NSP) | UPS | Rural | 2 | [6 empty] | 2 |  |  | 2 | 0
282 | KURICHEDU | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0804017 - MPPS BAYYAVARAM (SC) | PS | Rural | 1 | [7 empty] | 1 |  | 1 | 0
283 | KURICHEDU | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0804049 - MPPS KURICHEDU | PS | 1 | 1 |  |  | 1 | [6 empty] | 1 | 0
284 | KURICHEDU | KANDUKUR | DARSI | ADDANKI |  | 0804036 - MPPS PEDDA VARAM GEN |  |  | 1 | [7 empty] | 1
| KURICHEDU | [7 empty] | 10 | 0 | 0 | 2 | 0 | 0 | 0 | 3 | 5 | 0 | 9 | 0 | 0
285 | L.SAMUDRAM | KANDUKUR | KANDUKUR | KANDUKUR | Ramesh Babu | 0853014 - MPPS,VAKAMALLAVARI PALEM | PS | Rural | 2 | [6 empty] | 2
286 | L.SAMUDRAM | KANDUKUR | KANDUKUR | KANDUKUR | Ramesh Babu | 0853026 - MPPS,ANNEBOYANAPALLI HP | PS | Rural | 1 |  |  |  | 1
287 | L.SAMUDRAM | KANDUKUR | KANDUKUR | KANDUKUR | Ramesh Babu | 0853040 - MPPS,MUTYALAPADU ,H PALEM | PS | Rural | 1 | [6 empty] | 1
288 | L.SAMUDRAM | KANDUKUR | KANDUKUR | KANDUKUR | Ramesh Babu | 0853310-MPUPS,PEDAPAVANI | UPS | Rural | 1 | [5 empty] | 1
289 | L.SAMUDRAM | KANDUKUR | KANDUKUR | KANDUKUR | Ramesh Babu | 0853004 - MPPS,MUKTESWARAM | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | Due to not Deposition of amount in favour of SMC the work could not be taken up
290 | L.SAMUDRAM | KANDUKUR | KANDUKUR | KANDUKUR |  | 0853028 - MPPS,ANGIREKULAPADU(HP) |  |  | 1 | [7 empty] | 1
291 | L.SAMUDRAM | KANDUKUR | KANDUKUR | KANDUKUR |  | 0853302 - MPUPS,THIMMAREDDY PALEM |  |  | 3 | [7 empty] | 3
292 | L.SAMUDRAM | KANDUKUR | KANDUKUR | KANDUKUR |  | 0853310-MPUPS,PEDAPAVANI |  |  | 3 | [7 empty] | 3
293 | L.SAMUDRAM | KANDUKUR | KANDUKUR | KANDUKUR |  | 0853602 - K R ZPHS,LINGASAMUDRAM |  |  | 1 | [7 empty] | 1
| L.SAMUDRAM | [7 empty] | 14 | 0 | 0 | 0 | 1 | 0 | 1 | 3 | 9 | 0
294 | MADDIPADU | ONGOLE | S.N.PADU | ONGOLE | Vasu Rao | 0828032 - MPPS INAMANAMELLUR HW | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | No Site
295 | MADDIPADU | ONGOLE | S.N.PADU | ONGOLE | Vasu Rao | 0828055 - MPPS ANNANGI | PS | Rural | 1 |  |  |  | 1
296 | MADDIPADU | ONGOLE | S.N.PADU | ONGOLE | Vasu Rao | 0828006 - MPPS K.V.PALEM DPEP | PS | Rural | 1 | [7 empty] | 1 |  |  |  | Discussed with SMC. Work will be started next week | Site Dispute
297 | MADDIPADU | ONGOLE | S.N.PADU | ONGOLE |  | 0828010 - MPPS GAJULAPALEM |  |  | 1 |  |  |  | 1
298 | MADDIPADU | ONGOLE | S.N.PADU | ONGOLE |  | 0828601 - ZPHS KARUMUDIVARI PALEM |  |  | 3 |  |  |  | 3
| MADDIPADU | [7 empty] | 7 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 2 | 0
299 | MARKAPUR | MARKAPUR | MARKAPUR | MARKAPUR | MUZEEB | 0809007 - MPPS IDUPUR GEN | PS | Urban | 1 |  |  | 1
300 | MARKAPUR | MARKAPUR | MARKAPUR | MARKAPUR | MUZEEB | 0809008 - MPPS RAJUPALEM GEN | PS | Urban | 1 |  |  | 1
301 | MARKAPUR | MARKAPUR | MARKAPUR | MARKAPUR | MUZEEB | 0809009 - MPPS IDUPUR SC | PS | Urban | 1 |  |  | 1
302 | MARKAPUR | MARKAPUR | MARKAPUR | MARKAPUR | MUZEEB | 0809010 - MPPS DARIMADUGU URDU | PS | Urban | 1 |  |  | 1
303 | MARKAPUR | MARKAPUR | MARKAPUR | MARKAPUR | MUZEEB | 0809013 - MPPS NAIDUPALLI | PS | Urban | 1 |  | 1 | [9 empty] | Political Problam
304 | MARKAPUR | MARKAPUR | MARKAPUR | MARKAPUR | MUZEEB | 0809024 - MPPS RAYAVARAM GEN | PS | Urban | 1 | [6 empty] | 1
305 | MARKAPUR | MARKAPUR | MARKAPUR | MARKAPUR | MUZEEB | 0809027 - MPPS RAYAVARAM RS | PS | Urban | 2 | [6 empty] | 2
306 | MARKAPUR | MARKAPUR | MARKAPUR | MARKAPUR | MUZEEB | 0809029 - MPPS KANDIVARI PALLI | PS | Urban | 1 | [6 empty] | 1
307 | MARKAPUR | MARKAPUR | MARKAPUR | MARKAPUR | MUZEEB | 0809038 - MPPS SIVARAM PURAM | PS | Urban | 1 | [6 empty] | 1
308 | MARKAPUR | MARKAPUR | MARKAPUR | MARKAPUR | MUZEEB | 0809047 - MPPS THIPPAYA PALEM | PS | Urban | 2 |  |  | 1 |  |  |  |  | 1 |  |  |  |  | Dismantling
309 | MARKAPUR | MARKAPUR | MARKAPUR | MARKAPUR | MUZEEB | 0809053 - MPPS MITTIMEDIPALLI | PS | Urban | 1 | [6 empty] | 1
310 | MARKAPUR | MARKAPUR | MARKAPUR | MARKAPUR | MUZEEB | 0809081 - MPPS MODDULAPALLI | PS | Urban | 1 | [7 empty] | 1 |  |  |  |  | Not required
311 | MARKAPUR | MARKAPUR | MARKAPUR | MARKAPUR | MUZEEB | 0809083 - MPPS DARIMADUGU SC | PS | Urban | 1 | [6 empty] | 1
312 | MARKAPUR | MARKAPUR | MARKAPUR | MARKAPUR | MUZEEB | 0809304 - MPUPS PEDA YACHAVARAM | UPS | Urban | 3 |  |  |  | 2 |  |  | 1
313 | MARKAPUR | MARKAPUR | MARKAPUR | MARKAPUR | MUZEEB | 0809306 - MPUPS KONDEPALLI | UPS | Urban | 1 | [6 empty] | 1
314 | MARKAPUR | MARKAPUR | MARKAPUR | MARKAPUR | MUZEEB | 0809307 - MPUPS CHINTAKUNTA | UPS | Urban | 1 |  |  |  |  | 1
315 | MARKAPUR | MARKAPUR | MARKAPUR | MARKAPUR | MUZEEB | 0809317 - MPUPS NIKARAMPALLI | UPS | Urban | 2 | [6 empty] | 2
316 | MARKAPUR | MARKAPUR | MARKAPUR | MARKAPUR | MUZEEB | 0809320 - MPL UPS 1ST WARD | UPS | Urban | 1 |  |  |  | 1
317 | MARKAPUR | MARKAPUR | MARKAPUR | MARKAPUR | MUZEEB | 0809009 - MPPS IDUPUR SC | PS | Urban | 1 |  |  | 1
318 | MARKAPUR | MARKAPUR | MARKAPUR | MARKAPUR | MUZEEB | 0809042 - MPPS K.KOTHAPALLI | PS | Urban | 1 |  | 1
319 | MARKAPUR | MARKAPUR | MARKAPUR | MARKAPUR | MUZEEB | 0809024 - MPPS RAYAVARAM GEN | PS | 1 | 1 | [6 empty] | 1
320 | MARKAPUR | MARKAPUR | MARKAPUR | MARKAPUR | MUZEEB | 0809061 - MP VIVEKANANDA ELE S 6THW | PS | 1 | 1 | [6 empty] | 1
321 | MARKAPUR | MARKAPUR | MARKAPUR | MARKAPUR | MUZEEB | 0809307 - MPUPS CHINTAKUNTA | UPS | 1 | 1 |  |  |  |  | 1
322 | MARKAPUR | MARKAPUR | MARKAPUR | MARKAPUR | MUZEEB | 0809319 - EKALAVYA COLONY 5TH WARD | UPS | 1 | 1 | [6 empty] | 1
323 | MARKAPUR | MARKAPUR | MARKAPUR | MARKAPUR | MUZEEB | 0809320 - MPL UPS 1ST WARD | UPS | 1 | 1 |  |  |  | 1
324 | MARKAPUR | MARKAPUR | MARKAPUR | MARKAPUR | MUZEEB | 0809604 - ZPHS (GIRLS) 6TH WARD |  |  | 2 | [6 empty] | 2
325 | MARKAPUR | MARKAPUR | MARKAPUR | MARKAPUR | MUZEEB | 0809617 - APSWL TB CR HSC RAYAVARAM |  |  | 8 |  |  | 4 | 4
| MARKAPUR | [7 empty] | 40 | 0 | 2 | 10 | 8 | 2 | 0 | 16 | 2 | 0
326 | MARRIPUDI | KANDUKUR | KONDAPI | KANDUKUR | Ramesh Babu | 0830001 - MPPS GOSUKONDA AGRAHARAM | PS | Rural | 1 |  | 1
327 | MARRIPUDI | KANDUKUR | KONDAPI | KANDUKUR | Ramesh Babu | 0830002 - MPPS GOSUKONDA AGRAHARAM | PS | Rural | 1 |  |  |  | 1
328 | MARRIPUDI | KANDUKUR | KONDAPI | KANDUKUR | Ramesh Babu | 0830006 - MPPS GUNDLA SAMUDRAM | PS | Rural | 1 |  |  | 1
329 | MARRIPUDI | KANDUKUR | KONDAPI | KANDUKUR | Ramesh Babu | 0830011 - MPPS MARRIPUDI | PS | Rural | 1 | [6 empty] | 1
330 | MARRIPUDI | KANDUKUR | KONDAPI | KANDUKUR | Ramesh Babu | 0830012 - MPPS DUGGIREDDI PALEM | PS | Rural | 1 |  |  |  | 1
331 | MARRIPUDI | KANDUKUR | KONDAPI | KANDUKUR | Ramesh Babu | 0830017 - MPPS SIVARAYUNI PETA | PS | Rural | 1 |  |  | 1
332 | MARRIPUDI | KANDUKUR | KONDAPI | KANDUKUR | Ramesh Babu | 0830020 - MPPS CHILAMKURU | PS | Rural | 1 |  |  |  |  | 1
333 | MARRIPUDI | KANDUKUR | KONDAPI | KANDUKUR | Ramesh Babu | 0830022 - MPPS CHIMATA | PS | Rural | 1 |  |  |  | 1
334 | MARRIPUDI | KANDUKUR | KONDAPI | KANDUKUR | Ramesh Babu | 0830023 - MPPS OGIRALAVARI PALEM | PS | Rural | 1 |  |  |  |  | 1
335 | MARRIPUDI | KANDUKUR | KONDAPI | KANDUKUR | Ramesh Babu | 0830024 - MPPS VALLAYA PALEM | PS | Rural | 3 |  |  | 3
336 | MARRIPUDI | KANDUKUR | KONDAPI | KANDUKUR | Ramesh Babu | 0830033 - MPPS GARLA PETA | PS | Rural | 1 |  | 1
337 | MARRIPUDI | KANDUKUR | KONDAPI | KANDUKUR | Ramesh Babu | 0830045 - MPPS KELLAM PALLI | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | No site
338 | MARRIPUDI | KANDUKUR | KONDAPI | KANDUKUR | Ramesh Babu | 0830303 - MPUPS K G KANDRIKA | UPS | Rural | 1 |  |  |  | 1
339 | MARRIPUDI | KANDUKUR | KONDAPI | KANDUKUR | Ramesh Babu | 0830306 - MPUPS KUCHIPUDI | UPS | Rural | 3 | [7 empty] | 3 |  |  |  |  | Site to be procured
340 | MARRIPUDI | KANDUKUR | KONDAPI | KANDUKUR | Ramesh Babu | 0830307 - MPUPS SANNAMURU | UPS | Rural | 3 | [7 empty] | 3 |  |  |  |  | Site to be procured
341 | MARRIPUDI | KANDUKUR | KONDAPI | KANDUKUR | Ramesh Babu | 0830310 - MPUPS VEMA VARAM | UPS | Rural | 1 |  |  |  | 1
342 | MARRIPUDI | KANDUKUR | KONDAPI | KANDUKUR | Ramesh Babu | 0830003 - MPPS PINNIKAVARI PALEM | PS | Rural | 1 | [6 empty] | 1
343 | MARRIPUDI | KANDUKUR | KONDAPI | KANDUKUR | Ramesh Babu | 0830013 - MPPS POTTIREDDI PALEM | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | Not Requied
344 | MARRIPUDI | KANDUKUR | KONDAPI | KANDUKUR | Ramesh Babu | 0830036 - MPPS SIDDAREDDY PALLI | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | Not Requied
345 | MARRIPUDI | KANDUKUR | KONDAPI | KANDUKUR | Ramesh Babu | 0830037 - MPPS GARLA PETA | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | Not Requied
346 | MARRIPUDI | KANDUKUR | KONDAPI | KANDUKUR | Ramesh Babu | 0830018 - MPPS SIVARAYUNI PETA | PS | 1 | 1 |  |  |  | 1
347 | MARRIPUDI | KANDUKUR | KONDAPI | KANDUKUR | Ramesh Babu | 0830306 - MPUPS KUCHIPUDI | UPS | 1 | 1 | [7 empty] | 1 |  |  |  |  | Site procured
348 | MARRIPUDI | KANDUKUR | KONDAPI | KANDUKUR |  | 0830040 - MPPS JAGGARAJU PALEM |  |  | 2 |  |  | 2
| MARRIPUDI | [7 empty] | 30 | 0 | 2 | 7 | 6 | 2 | 0 | 2 | 11 | 0 | 0 | 0 | 0
349 | MARTUR | ONGOLE | PARCHUR | PARCHUR |  | 0820004 - MPPS RAJUPALEM | PS | Rural | 1 | 5.3 |  | 1
350 | MARTUR | ONGOLE | PARCHUR | PARCHUR |  | 0820012 - MPPS MARTUR RJST | PS | Rural | 1 | 5.3 |  | 1
351 | MARTUR | ONGOLE | PARCHUR | PARCHUR |  | 0820014 - MPPS PEERLACHAVADI | PS | Rural | 1 | 5.3 | [6 empty] | 1 |  |  |  |  | No site
352 | MARTUR | ONGOLE | PARCHUR | PARCHUR |  | 0820021 - MPPS DARSI (URDU) | PS | Rural | 1 | 5.3 | [6 empty] | 1 |  |  |  |  | Agent not fixed
353 | MARTUR | ONGOLE | PARCHUR | PARCHUR |  | 0820023 - MPPS VALAPARLA (HW) | PS | Rural | 1 | 5.3 |  |  | 1
354 | MARTUR | ONGOLE | PARCHUR | PARCHUR |  | 0820024 - MPPS VALAPARLA (TANK) | PS | Rural | 1 | 5.3 |  | 1
355 | MARTUR | ONGOLE | PARCHUR | PARCHUR |  | 0820027 - MPPS LAKKAVARAM | PS | Rural | 1 | 5.3 | [5 empty] | 1
356 | MARTUR | ONGOLE | PARCHUR | PARCHUR |  | 0820028 - MPPS CHIMMIRIBANDA | PS | Rural | 1 | 5.3 | [5 empty] | 1
357 | MARTUR | ONGOLE | PARCHUR | PARCHUR |  | 0820035 - MPPS KOLALA PUDI (AA) | PS | Rural | 2 | 10.6 | [5 empty] | 2
358 | MARTUR | ONGOLE | PARCHUR | PARCHUR |  | 0820306 - MPUPS CHIMMIRIBANDA | UPS | Rural | 1 | 5.3 |  |  |  | 1
359 | MARTUR | ONGOLE | PARCHUR | PARCHUR |  | 0820002 - MPPS N R PALLI SC | PS | Rural | 1 | 5.3 |  | 1
360 | MARTUR | ONGOLE | PARCHUR | PARCHUR |  | 0820008 - MPPS AMBEDKAR NAGAR |  |  | 1 | [7 empty] | 1
361 | MARTUR | ONGOLE | PARCHUR | PARCHUR |  | 0820013 - MPPS GUTTIPATI H NAGAR |  |  | 1 | [7 empty] | 1
362 | MARTUR | ONGOLE | PARCHUR | PARCHUR |  | 0820026 - MPPS VALAPARLA (URDU) |  |  | 1 |  |  | 1
363 | MARTUR | ONGOLE | PARCHUR | PARCHUR |  | 0820604 - ZPHS DRONADULA |  |  | 2 | [7 empty] | 2
364 | MARTUR | ONGOLE | PARCHUR | PARCHUR |  | 0820605 - ZPHS KOLALA PUDI |  |  | 1 |  |  | 1
| MARTUR | [7 empty] | 18 | 63.6 | 0 | 6 | 1 | 1 | 0 | 4 | 6 | 0 | 0 | 0 | 0
365 | MUNDLAMURU | KANDUKUR | DARSI | ADDANKI | P.Subba Rao | 0814005 - MPPS BHEEMAVARAM SC | PS | Rural | 1 |  |  |  | 1 | [5 empty] | 1 | 0
366 | MUNDLAMURU | KANDUKUR | DARSI | ADDANKI | P.Subba Rao | 0814015 - MPPS U M PURAM NORTH | PS | Rural | 1 |  |  |  | 1 | [5 empty] | 1 | 0
367 | MUNDLAMURU | KANDUKUR | DARSI | ADDANKI | P.Subba Rao | 0814018 - MPPS KOTHA MARELLA | PS | Rural | 1 | [7 empty] | 1 |  | 1 | 0 |  | Dismantling
368 | MUNDLAMURU | KANDUKUR | DARSI | ADDANKI | P.Subba Rao | 0814019 - MPPS MARELLA (HW) | PS | Rural | 1 |  |  | 1 | [6 empty] | 1 | 0
369 | MUNDLAMURU | KANDUKUR | DARSI | ADDANKI | P.Subba Rao | 0814020 - MPPS GANGANNAPALEM | PS | Rural | 1 | [7 empty] | 1 |  | 1 | 0
370 | MUNDLAMURU | KANDUKUR | DARSI | ADDANKI | P.Subba Rao | 0814026 - MPPS PEDDARAVIPADU | PS | Rural | 1 |  |  | 1 | [6 empty] | 1 | 0
371 | MUNDLAMURU | KANDUKUR | DARSI | ADDANKI | P.Subba Rao | 0814035 - MPPS BRUNDAVANAM (DARSI) | PS | Rural | 1 | [6 empty] | 1 |  |  | 1 | 0
372 | MUNDLAMURU | KANDUKUR | DARSI | ADDANKI | P.Subba Rao | 0814037 - MPPS PULIPADU THANDA | PS | Rural | 1 | [6 empty] | 1 |  |  | 1 | 0
373 | MUNDLAMURU | KANDUKUR | DARSI | ADDANKI | P.Subba Rao | 0814041 - MPPS PEDAVULLAGALLU | PS | Rural | 1 | [6 empty] | 1 |  |  | 1 | 0
374 | MUNDLAMURU | KANDUKUR | DARSI | ADDANKI | P.Subba Rao | 0814044 - MPPS PASUPUGALLU AA | PS | Rural | 1 | [7 empty] | 1 |  | 1 | 0
375 | MUNDLAMURU | KANDUKUR | DARSI | ADDANKI | P.Subba Rao | 0814045 - MPPS MAKKENAVARIPALEM | PS | Rural | 1 | [6 empty] | 1 |  |  | 1 | 0
376 | MUNDLAMURU | KANDUKUR | DARSI | ADDANKI | P.Subba Rao | 0814052 - MPPS POLAVARAM | PS | Rural | 3 | [7 empty] | 3 |  | 3 | 0
377 | MUNDLAMURU | KANDUKUR | DARSI | ADDANKI | P.Subba Rao | 0814054 - MPPS MUNDLAMUR HW | PS | Rural | 1 |  |  | 1 | [6 empty] | 1 | 0
378 | MUNDLAMURU | KANDUKUR | DARSI | ADDANKI | P.Subba Rao | 0814055 - MPPS VEMULA | PS | Rural | 2 |  |  |  |  | 1 |  | 1 |  |  | 2 | 0
379 | MUNDLAMURU | KANDUKUR | DARSI | ADDANKI | P.Subba Rao | 0814057-MPPS PEDAVULLAGALLU H.W | PS | Rural | 1 |  |  | 1 | [6 empty] | 1 | 0
380 | MUNDLAMURU | KANDUKUR | DARSI | ADDANKI | P.Subba Rao | 0814304 - MPUPS VEMULABANDA | UPS | Rural | 1 | [6 empty] | 1 |  |  | 1 | 0
381 | MUNDLAMURU | KANDUKUR | DARSI | ADDANKI | P.Subba Rao | 0814308 - MPUPS SINGANA PALEM | UPS | Rural | 1 |  |  | 1 | [6 empty] | 1 | 0
382 | MUNDLAMURU | KANDUKUR | DARSI | ADDANKI | P.Subba Rao | 0814309 - MPUPS NAYUDUPALEM | UPS | Rural | 2 | [7 empty] | 2 |  | 2 | 0
383 | MUNDLAMURU | KANDUKUR | DARSI | ADDANKI | P.Subba Rao | 0814310 - MPUPS KELLAM PALLI | UPS | Rural | 1 | [6 empty] | 1 |  |  | 1 | 0
384 | MUNDLAMURU | KANDUKUR | DARSI | ADDANKI | P.Subba Rao | 0814012 - MPPS R.G.R. NAGAR | PS | Rural | 1 | [6 empty] | 1 |  |  | 1 | 0
385 | MUNDLAMURU | KANDUKUR | DARSI | ADDANKI | P.Subba Rao | 0814053 - MPPS PULIPADU BRM GUTTA | PS | Rural | 1 | [6 empty] | 1 |  |  | 1 | 0
386 | MUNDLAMURU | KANDUKUR | DARSI | ADDANKI | P.Subba Rao | 0814015 - MPPS U M PURAM NORTH | PS | 1 | 1 |  |  |  | 1 | [5 empty] | 1 | 0
388 | MUNDLAMURU | KANDUKUR | DARSI | ADDANKI | P.Subba Rao | 0814601 - ZPHS EDARA |  |  | 2 | [6 empty] | 2
389 | MUNDLAMURU | KANDUKUR | DARSI | ADDANKI |  | 0814311 - MPUPS POLAVARAM |  |  | 1 | [7 empty] | 1
390 | MUNDLAMURU | KANDUKUR | DARSI | ADDANKI |  | 0814605 - ZPHS VEMULA |  |  | 2 | [7 empty] | 2
| MUNDLAMURU | [7 empty] | 31 | 0 | 0 | 5 | 3 | 1 | 0 | 11 | 11 | 0
391 | N.G.PADU | ONGOLE | S.N.PADU | ONGOLE | Vasu Rao | 0845028 - MPPS,UPUGUNDR SATRAM BAZ | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | Dismantling
392 | N.G.PADU | ONGOLE | S.N.PADU | ONGOLE | Vasu Rao | 0845047 - MPPS,VINODARAYUNI PALEM | PS | Rural | 1 | [6 empty] | 1
393 | N.G.PADU | ONGOLE | S.N.PADU | ONGOLE | Vasu Rao | 0845308 - M.P.U.PS,OMMEVARAM | UPS | Rural | 2 | [7 empty] | 2 |  |  |  |  | political dispute
394 | N.G.PADU | ONGOLE | S.N.PADU | ONGOLE |  | 0845307 - MPUPS,K.CH.UPPALA PADU |  |  | 1 | [7 empty] | 1
| N.G.PADU | [7 empty] | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 0
395 | ONGOLE | ONGOLE | ONGOLE | ONGOLE | J.V.Ramana Murthy | 0844009 - MPPS,ULICHI (CE) | PS | Rural | 1 | [6 empty] | 1
396 | ONGOLE | ONGOLE | ONGOLE | ONGOLE | J.V.Ramana Murthy | 0844012 - MPPS,DEVARAM PADU (HW) | PS | Rural | 1 | [6 empty] | 1
397 | ONGOLE | ONGOLE | ONGOLE | ONGOLE | J.V.Ramana Murthy | 0844021 - MPPS,MUKTHINUTHALA PADU | PS | Urban | 1 |  |  |  |  | 1
398 | ONGOLE | ONGOLE | ONGOLE | ONGOLE | J.V.Ramana Murthy | 0844042 - SKYMPL.ELES,GOPALANAGARAM | PS | Urban | 1 | [6 empty] | 1
399 | ONGOLE | ONGOLE | ONGOLE | ONGOLE | J.V.Ramana Murthy | 0844085 - GOVT PS(TW), MARUTHINAGAR | PS | Urban | 1 | [6 empty] | 1
400 | ONGOLE | ONGOLE | ONGOLE | ONGOLE | J.V.Ramana Murthy | 0844026 - MPPS,ONGOLE ,P H COLONY | PS | Urban | 1 | [6 empty] | 1
401 | ONGOLE | ONGOLE | ONGOLE | ONGOLE | J.V.Ramana Murthy | 0844603 - Govt.HS (G), BANDLAMITTA |  |  | 2 | [6 empty] | 2
| ONGOLE | [7 empty] | 8 | 0 | 0 | 0 | 0 | 1 | 0 | 7 | 0 | 0
402 | P.C.PALLI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0840010 - MPPS,CH. GOGULA PALLE | PS | Rural | 1 |  |  |  |  | 1
403 | P.C.PALLI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0840012 - MPPS,RAMAPURAM | PS | Rural | 1 |  |  |  |  | 1
404 | P.C.PALLI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0840013 - MPPS,CHINTHALA PALEM | PS | Rural | 1 | [6 empty] | 1
405 | P.C.PALLI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0840019 - MPPS,NEREDU PALLI | PS | Rural | 1 |  |  |  | 1
406 | P.C.PALLI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0840036 - MPPS,PEDAVARI MADUGU | PS | Rural | 1 |  |  | 1
407 | P.C.PALLI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0840041 - MPPS,MULEVARIPALLI | PS | Rural | 1 | [6 empty] | 1
408 | P.C.PALLI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0840046 - MPPS,DIVAKARA PURAM | PS | Rural | 1 | [6 empty] | 1
409 | P.C.PALLI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0840047 - MPPS,VENGALAYAPALLI | PS | Rural | 1 | [6 empty] | 1
410 | P.C.PALLI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0840054 - MPPS,P.IRLA PADU, JC CLY | PS | Rural | 1 | [6 empty] | 1
411 | P.C.PALLI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0840306 - MPUPS,G.NAGANNA PALEM | UPS | Rural | 1 | [6 empty] | 1
412 | P.C.PALLI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0840309 - M P U PS,THURAKAPALLI | UPS | Rural | 1 | [6 empty] | 1
413 | P.C.PALLI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0840008 - MPPS,CHINA BATTUPALLI | PS | Rural | 1 |  |  |  |  | 1
414 | P.C.PALLI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0840040 - MPPS,PILLIVARI PALLI | PS | Rural | 1 | [6 empty] | 1
415 | P.C.PALLI | KANDUKUR | KANIGIRI | KANIGIRI |  | 0840309 - M P U PS,THURAKAPALLI |  |  | 1 | [7 empty] | 1
| P.C.PALLI | [7 empty] | 14 | 0 | 0 | 1 | 1 | 3 | 0 | 8 | 1 | 0
416 | P.DORNALA | MARKAPUR | Y.PALEM | MARKAPUR | THIMMAREDDY | 0807002 - MPPS WEST BOMMALA PURAM | PS | Rural | 1 |  | 1
417 | P.DORNALA | MARKAPUR | Y.PALEM | MARKAPUR | THIMMAREDDY | 0807006 - MPPS HASANABAD | PS | Rural | 2 |  |  |  |  | 2
418 | P.DORNALA | MARKAPUR | Y.PALEM | MARKAPUR | THIMMAREDDY | 0807016 - MPPS YEGUVA CHERLO PALLI | PS | Rural | 1 |  |  | 1
419 | P.DORNALA | MARKAPUR | Y.PALEM | MARKAPUR | THIMMAREDDY | 0807025 - MPPS CHINAGUDIPADU | PS | Rural | 1 |  |  | 1
420 | P.DORNALA | MARKAPUR | Y.PALEM | MARKAPUR | THIMMAREDDY | 0807026 - MPPS KATA KANI PALLI | PS | Rural | 1 |  |  |  |  | 1
421 | P.DORNALA | MARKAPUR | Y.PALEM | MARKAPUR | THIMMAREDDY | 0807028 - MPPS RAMACHANDRA KOTA | PS | Rural | 2 |  |  | 1 |  |  |  | 1
422 | P.DORNALA | MARKAPUR | Y.PALEM | MARKAPUR | THIMMAREDDY | 0807032 - GOVT.AS MARRIPALEM (R.F) | PS | Rural | 2 |  |  |  | 2
423 | P.DORNALA | MARKAPUR | Y.PALEM | MARKAPUR | THIMMAREDDY | 0807066-GOVT PS BALIJAPALLI | PS | Rural | 1 | [7 empty] | 1
424 | P.DORNALA | MARKAPUR | Y.PALEM | MARKAPUR | THIMMAREDDY | 0807309 - MPUPS CHINTALA AGRAHARAM | UPS | Rural | 4 |  |  | 4 | [8 empty] | MRO promissed to give possession certificate
425 | P.DORNALA | MARKAPUR | Y.PALEM | MARKAPUR | THIMMAREDDY | 0807037 - GOVT PSCHINA ARUTLA (R.F) | PS | Rural | 1 | [7 empty] | 1
426 | P.DORNALA | MARKAPUR | Y.PALEM | MARKAPUR | THIMMAREDDY | 0807061-GOVT PS AYYANAKOTA | PS | Rural | 1 | [7 empty] | 1
427 | P.DORNALA | MARKAPUR | Y.PALEM | MARKAPUR | THIMMAREDDY | 0807068-GOVT PS PAMUKUMADUGU | PS | Rural | 1 | [7 empty] | 1
428 | P.DORNALA | MARKAPUR | Y.PALEM | MARKAPUR | THIMMAREDDY | 0807032 - GOVT.AS MARRIPALEM (R.F) | PS | 1 | 1 |  |  |  | 1
| P.DORNALA | [7 empty] | 19 | 0 | 1 | 7 | 3 | 3 | 0 | 1 | 4 | 0
429 | PAMUR | KANDUKUR | KANIGIRI | KANIGIRI |  | 0852011 - MPPS,GUMMALAMPADU (SC) | PS | Rural | 1 | [6 empty] | 1
430 | PAMUR | KANDUKUR | KANIGIRI | KANIGIRI |  | 0852015 - MPPS,KOTHAPALLI | PS | Rural | 1 |  | 1
431 | PAMUR | KANDUKUR | KANIGIRI | KANIGIRI |  | 0852016 - MPPS,RAVIGUNTAPALLI | PS | Rural | 1 |  | 1
432 | PAMUR | KANDUKUR | KANIGIRI | KANIGIRI |  | 0852019 - MPPS,HP OF INIMERLA | PS | Rural | 1 | [6 empty] | 1
433 | PAMUR | KANDUKUR | KANIGIRI | KANIGIRI |  | 0852021 - MPPS,INIMERLA (AAW) | PS | Rural | 1 | [6 empty] | 1
434 | PAMUR | KANDUKUR | KANIGIRI | KANIGIRI |  | 0852029 - MPPS,THATHAYAPALLI | PS | Rural | 1 | [6 empty] | 1
435 | PAMUR | KANDUKUR | KANIGIRI | KANIGIRI |  | 0852031 - MPPS,VENKATAPURAM | PS | Rural | 1 | [6 empty] | 1
436 | PAMUR | KANDUKUR | KANIGIRI | KANIGIRI |  | 0852035 - MPPS,02ND WARD | PS | Rural | 1 | [6 empty] | 1
437 | PAMUR | KANDUKUR | KANIGIRI | KANIGIRI |  | 0852044 - MPPS,PAMUR S T COLONY | PS | Rural | 1 | [6 empty] | 1
438 | PAMUR | KANDUKUR | KANIGIRI | KANIGIRI |  | 0852067 - MPPS,AYYANNAKOTA | PS | Rural | 1 |  |  |  | 1
439 | PAMUR | KANDUKUR | KANIGIRI | KANIGIRI |  | 0852070 - MPPS,RAJASAHEBPETA | PS | Rural | 1 |  |  |  |  | 1
440 | PAMUR | KANDUKUR | KANIGIRI | KANIGIRI |  | 0852075 - MPPS,RAGHUNADHA PURAM | PS | Rural | 1 | [6 empty] | 1
441 | PAMUR | KANDUKUR | KANIGIRI | KANIGIRI |  | 0852085 - MPPS,RENIMADUGU (OLD) | PS | Rural | 1 |  |  |  | 1
442 | PAMUR | KANDUKUR | KANIGIRI | KANIGIRI |  | 0852086 - MPPS,AKKAMPETA | PS | Rural | 1 |  |  |  |  | 1
443 | PAMUR | KANDUKUR | KANIGIRI | KANIGIRI |  | 0852304 - MPUPS,BALIJAPALEM | UPS | Rural | 1 |  |  | 1
444 | PAMUR | KANDUKUR | KANIGIRI | KANIGIRI |  | 0852008 - MPPS,CHATTUMADUGU(H) | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | Site dispute
445 | PAMUR | KANDUKUR | KANIGIRI | KANIGIRI |  | 0852040 - MPPS,GOPALAPURAM ( SC ) | PS | Rural | 1 | [6 empty] | 1
446 | PAMUR | KANDUKUR | KANIGIRI | KANIGIRI |  | 0852047 - MPPS,JANGALAPALLI | PS | Rural | 1 |  |  | 1
447 | PAMUR | KANDUKUR | KANIGIRI | KANIGIRI |  | 0852048 - MPPS,POTHAVARAM | PS | Rural | 1 |  |  | 1
448 | PAMUR | KANDUKUR | KANIGIRI | KANIGIRI |  | 0852051 - MPPS,TIRAGANDLA DINNE | PS | Rural | 1 |  |  | 1
449 | PAMUR | KANDUKUR | KANIGIRI | KANIGIRI |  | 0852074 - MPPS,BOTLAGUDUR RVKOSTALU | PS | Rural | 1 |  |  |  | 1
| PAMUR | [7 empty] | 21 | 0 | 2 | 4 | 3 | 2 | 0 | 9 | 1 | 0 | 0 | 0 | 0
450 | PARCHUR | ONGOLE | PARCHUR | PARCHUR |  | 0821003 - MPPS A.B.V.PALEM | PS | Rural | 1 | 5.3 |  |  |  | 1
451 | PARCHUR | ONGOLE | PARCHUR | PARCHUR |  | 0821017 - MPPS KOTHAPALEM | PS | Rural | 1 | 5.3 | [5 empty] | 1
452 | PARCHUR | ONGOLE | PARCHUR | PARCHUR |  | 0821034 - MPPS CH.B.V.PALEM | PS | Rural | 1 | 5.3 | [5 empty] | 1
453 | PARCHUR | ONGOLE | PARCHUR | PARCHUR |  | 0821037 - MPPS NUTHALAPADU (URDU) | PS | Rural | 1 | 5.3 | [5 empty] | 1
454 | PARCHUR | ONGOLE | PARCHUR | PARCHUR |  | 0821039 - MPPS KURAPPALEM |  |  | 1 | [7 empty] | 1
455 | PARCHUR | ONGOLE | PARCHUR | PARCHUR |  | 0821303 - MPUPS NUTHALAPADU |  |  | 1 | [7 empty] | 1
| PARCHUR | [7 empty] | 6 | 21.2 | 0 | 0 | 0 | 1 | 0 | 3 | 2 | 0
456 | PEDAARAVEEDU | MARKAPUR | Y.PALEM | MARKAPUR | THIMMAREDDY | 0806001 - MPPS SANIKAVARAM | PS | Rural | 1 |  |  | 1
457 | PEDAARAVEEDU | MARKAPUR | Y.PALEM | MARKAPUR | THIMMAREDDY | 0806004 - MPPS CHATLAMADA | PS | Rural | 1 |  |  |  |  | 1
458 | PEDAARAVEEDU | MARKAPUR | Y.PALEM | MARKAPUR | THIMMAREDDY | 0806007 - MPPS RAJAMPALLI | PS | Rural | 1 | [6 empty] | 1
459 | PEDAARAVEEDU | MARKAPUR | Y.PALEM | MARKAPUR | THIMMAREDDY | 0806008 - MPPS REGUMANIPALLI | PS | Rural | 1 | [6 empty] | 1
460 | PEDAARAVEEDU | MARKAPUR | Y.PALEM | MARKAPUR | THIMMAREDDY | 0806014 - MPPS THANGIRALLA PALLI SP | PS | Rural | 2 |  |  |  | 2
461 | PEDAARAVEEDU | MARKAPUR | Y.PALEM | MARKAPUR | THIMMAREDDY | 0806016 - MPPS THOKAPALLI SPL | PS | Rural | 2 |  | 2
462 | PEDAARAVEEDU | MARKAPUR | Y.PALEM | MARKAPUR | THIMMAREDDY | 0806025 - MPPS PRAGALLAPADU | PS | Rural | 2 | [6 empty] | 2
463 | PEDAARAVEEDU | MARKAPUR | Y.PALEM | MARKAPUR | THIMMAREDDY | 0806026 - MPPS GOBBURU SC BC | PS | Rural | 1 | [6 empty] | 1
464 | PEDAARAVEEDU | MARKAPUR | Y.PALEM | MARKAPUR | THIMMAREDDY | 0806042 - GOVT.AS CHINTHALAMUDIPI | PS | Rural | 2 | [7 empty] | 2 |  |  |  |  | Submerssion under Velugonda Project
465 | PEDAARAVEEDU | MARKAPUR | Y.PALEM | MARKAPUR | THIMMAREDDY | 0806303 - MPUPS THANGIRALLA PALLI | UPS | Rural | 1 | [6 empty] | 1
466 | PEDAARAVEEDU | MARKAPUR | Y.PALEM | MARKAPUR | THIMMAREDDY | 0806305 - MPUPS PUCHAKAYALAPALLI | UPS | Rural | 1 |  |  |  | 1
467 | PEDAARAVEEDU | MARKAPUR | Y.PALEM | MARKAPUR | THIMMAREDDY | 0806307 - MPUPS THOKA PALLI | UPS | Rural | 1 |  |  |  |  | 1
468 | PEDAARAVEEDU | MARKAPUR | Y.PALEM | MARKAPUR | THIMMAREDDY | 0806308 - MPUPS BADVEEDU | UPS | Rural | 1 |  |  |  |  | 1
469 | PEDAARAVEEDU | MARKAPUR | Y.PALEM | MARKAPUR | THIMMAREDDY | 0806023 - MPPS B CHERLO PALLI GEN | PS | 1 | 1 | [6 empty] | 1
470 | PEDAARAVEEDU | MARKAPUR | Y.Palem | MARKAPUR |  | 0806602 - ZPHS SANIKAVARAM | 1 |  | 1 |  |  | 1
471 | PEDAARAVEEDU | MARKAPUR | Y.Palem | MARKAPUR |  | 0806603 - ZPHS OBULAKKAPALLI | 1 |  | 1 |  | 1
472 | PEDAARAVEEDU | MARKAPUR | Y.Palem | MARKAPUR |  | 0806604 - ZPHS YENUGULADINNEPADU | 3 |  | 3 |  |  | 3
| PEDAARAVEEDU | [7 empty] | 23 | 0 | 3 | 5 | 3 | 3 | 0 | 7 | 2 | 0
473 | PODILI | KANDUKUR | MARKAPUR | ONGOLE |  | 0812004 - MPPS CHIDAMBARA PALLI | PS | Rural | 1 | [6 empty] | 1
474 | PODILI | KANDUKUR | MARKAPUR | ONGOLE |  | 0812006 - MPPS KUNCHEPALLI | PS | Rural | 1 | [6 empty] | 1
475 | PODILI | KANDUKUR | MARKAPUR | ONGOLE |  | 0812015 - MPPS THUMMAGUNTA(AA) | PS | Rural | 1 |  |  |  |  | 1
476 | PODILI | KANDUKUR | MARKAPUR | ONGOLE |  | 0812018 - MPPS KONDAYA PALEM | PS | Rural | 1 | [6 empty] | 1
477 | PODILI | KANDUKUR | MARKAPUR | ONGOLE |  | 0812035 - MPPS PODILI URDU | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | Dismantling
478 | PODILI | KANDUKUR | MARKAPUR | ONGOLE |  | 0812046 - MPPS KOTHAPALEM | PS | Rural | 1 | [6 empty] | 1
479 | PODILI | KANDUKUR | MARKAPUR | ONGOLE |  | 0812055 - MPPS CHINTHAGUMPALLI | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | Not Requied
480 | PODILI | KANDUKUR | MARKAPUR | ONGOLE |  | 0812057 - MPPS THALAMALLA | PS | Rural | 1 | [6 empty] | 1
481 | PODILI | KANDUKUR | MARKAPUR | ONGOLE |  | 0812058 - MPPS THALAMALLA HW | PS | Rural | 1 | [6 empty] | 1
482 | PODILI | KANDUKUR | MARKAPUR | ONGOLE |  | 0812060 - MPPS UPPALA PADU | PS | Rural | 1 | [6 empty] | 1
483 | PODILI | KANDUKUR | MARKAPUR | ONGOLE |  | 0812061-MPPS GOGINENIVARI (HW) | PS | Rural | 1 | [6 empty] | 1
484 | PODILI | KANDUKUR | MARKAPUR | ONGOLE |  | 0812064 - MPPS T.SALLURU | PS | Rural | 1 |  |  |  |  | 1
485 | PODILI | KANDUKUR | MARKAPUR | ONGOLE |  | 0812319 - MPUPS OBULAKKA PALLI | UPS | Rural | 1 | [6 empty] | 1
486 | PODILI | KANDUKUR | MARKAPUR | ONGOLE |  | 0812034 - MPPS PODILI HW | PS | Rural | 1 | [6 empty] | 1
487 | PODILI | KANDUKUR | MARKAPUR | ONGOLE |  | 0812063 - MPPS NALLAREDDY PALEM | PS | Rural | 1 | [6 empty] | 1
488 | PODILI | KANDUKUR | MARKAPUR | ONGOLE |  | 0812015 - MPPS THUMMAGUNTA(AA) |  |  | 1 |  |  |  | 1
489 | PODILI | KANDUKUR | MARKAPUR | ONGOLE |  | 0812030 - MPPS RAMAYANAM KANDRIKA |  |  | 1 |  |  |  | 1
490 | PODILI | KANDUKUR | MARKAPUR | ONGOLE |  | 0812044 - MPPS YANADI COLONY |  |  | 1 |  |  |  | 1
| PODILI | [7 empty] | 18 | 0 | 0 | 0 | 3 | 2 | 0 | 11 | 2 | 0
491 | PONNALURU | KANDUKUR | KONDAPI | KANDUKUR | Ramesh Babu | 0841007 - MPPS,RAJOLUPADU | PS | Rural | 1 |  |  | 1
492 | PONNALURU | KANDUKUR | KONDAPI | KANDUKUR | Ramesh Babu | 0841019 - MPPS,VELLATURU | PS | Rural | 2 |  | 2
493 | PONNALURU | KANDUKUR | KONDAPI | KANDUKUR | Ramesh Babu | 0841045 - MP PS,CHENNIPADU | PS | Rural | 1 |  |  | 1
494 | PONNALURU | KANDUKUR | KONDAPI | KANDUKUR | Ramesh Babu | 0841009 - MPPS,MANGINAPADU | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | Not Requied
495 | PONNALURU | KANDUKUR | KONDAPI | KANDUKUR | Ramesh Babu | 0841010 - MPPS,EDURUVARI PALEM | PS | Rural | 1 |  | 1
496 | PONNALURU | KANDUKUR | KONDAPI | KANDUKUR | Ramesh Babu | 0841012 - MPPS,THETUPETA | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | Not Requied
497 | PONNALURU | KANDUKUR | KONDAPI | KANDUKUR | Ramesh Babu | 0841029 - MPPS,RAMANNAPALEM | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | No site
498 | PONNALURU | KANDUKUR | KONDAPI | KANDUKUR |  | 0841307 - MPUP S,MALEPADU |  |  | 1 | [7 empty] | 1
499 | PONNALURU | KANDUKUR | KONDAPI | KANDUKUR |  | 0841606 - ZPHS,CHENNIPADU |  |  | 1 | [7 empty] | 1
| PONNALURU | [7 empty] | 10 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 5 | 0
500 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802001 - MPPS MARRIVEMULA | PS | Rural | 1 | [6 empty] | 1
501 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802006 - MPPS PULLALA CHERUVU (BC) | PS | Rural | 1 | [6 empty] | 1
502 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802009 - MPPS PULLALA CHERUVU (SC) | PS | Rural | 1 | [6 empty] | 1
503 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802012 - MPPS SUDDAKURAVA THANDA | PS | Rural | 1 | [6 empty] | 1
504 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802013 - MPPS VENKATAREDDY PALLI | PS | Rural | 1 | [6 empty] | 1
505 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802014 - MPPS PITCHIRAJ CHERVU THA | PS | Rural | 1 |  |  | 1
506 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802016 - MPPS NARAJAMULA | PS | Rural | 1 | [6 empty] | 1
507 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802018 - MPPS KUNDAMPALLI | PS | Rural | 1 |  | 1
508 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802020 - MPPS M YERRABALEM | PS | Rural | 2 |  |  | 2
509 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802022 - MPPS CHENNAMPALLI | PS | Rural | 2 | [6 empty] | 2
510 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802023 - MPPS C.KOTHAPALLI | PS | Rural | 2 | [6 empty] | 2
511 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802024 - MPPS NAYUDUPALEM | PS | Rural | 1 |  |  | 1
512 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802027 - MPPS KAVALA KUNTLA | PS | Rural | 1 | [6 empty] | 1
513 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802028 - MPPS THELLAGATLA | PS | Rural | 1 | [6 empty] | 1
514 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802029 - MPPS BEEMANENI PALLI | PS | Rural | 1 | [6 empty] | 1
515 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802030 - MPPS SINGUPALLI | PS | Rural | 1 | [6 empty] | 1
516 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802035 - MPPS RENTAPALLI | PS | Rural | 2 | [7 empty] | 2 |  |  |  |  | Dismantling
517 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802036 - MPPS SIDDENA PALEM | PS | Rural | 2 | [6 empty] | 2
518 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802037 - MPPS RENTAPALLI THANDA | PS | Rural | 1 |  | 1 | [9 empty] | Dispute in procurement of site
519 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802039 - Govt. ST PS NARAJ THANDA | PS | Rural | 1 |  |  | 1
520 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802060 -MPPS CHOWTAPA CHARLA(SC) | PS | Rural | 1 | [6 empty] | 1
521 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802061 - GOVT PS AKKAPALEM | PS | Rural | 2 |  |  | 2
522 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802064-GOVT PS KOMOROLE | PS | Rural | 1 | [6 empty] | 1
523 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802067-MPPS CHAPALA MADUGU | PS | Rural | 2 |  |  | 2 | [8 empty] | Site to be procured by villagers
524 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802305 - MPUPS MUTUKULA | UPS | Rural | 3 | [6 empty] | 3
525 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802309 - MPUPS SATHA KODU | UPS | Rural | 3 | [6 empty] | 3
526 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802015 - MPPS PATHA CHERVU THANDA | PS | Rural | 1 | [6 empty] | 1
527 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802051 - GOVT PS(T.W) UMMADIVARAM | PS | Rural | 1 |  |  | 1
528 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802063 - GOVT PS GANDHIBAVI GUDEM | PS | Rural | 1 | [6 empty] | 1
529 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802001 - MPPS MARRIVEMULA | PS | 1 | 1 | [6 empty] | 1
530 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802006 - MPPS PULLALA CHERUVU (BC) | PS | 1 | 1 |  |  | 1
531 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802027 - MPPS KAVALA KUNTLA | PS | 1 | 1 | [6 empty] | 1
532 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802028 - MPPS THELLAGATLA | PS | 1 | 1 | [6 empty] | 1
533 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802036 - MPPS SIDDENA PALEM | PS | 1 | 1 | [6 empty] | 1
534 | PULLALACHERUVU | MARKAPUR | Y.PALEM | MARKAPUR | SIVA RAM | 0802603 - ZPHS PIDIKITIVARI PALLI |  |  | 2 | [6 empty] | 2
| PULLALACHERUVU | [7 empty] | 47 | 0 | 2 | 11 | 0 | 0 | 0 | 32 | 2 | 0
535 | RACHERLA | MARKAPUR | GIDDALUR | KANIGIRI |  | 0835026 - MPPS,RACHERLA (SPG) | PS | Rural | 1 | [6 empty] | 1 | [5 empty] | Not Requied
536 | RACHERLA | MARKAPUR | GIDDALUR | KANIGIRI |  | 0835029 - MPPS,GUDIMETTA | PS | Rural | 1 |  | 1
537 | RACHERLA | MARKAPUR | GIDDALUR | KANIGIRI |  | 0835035 - MPPS,RANGAREDDY PALLI | PS | Rural | 1 |  |  | 1
538 | RACHERLA | MARKAPUR | GIDDALUR | KANIGIRI |  | 0835037 - MPPS,SATYAVOLU | PS | Rural | 1 |  | 1
539 | RACHERLA | MARKAPUR | GIDDALUR | KANIGIRI |  | 0835010 - MPPS,J.P.CHERUVU (MAIN) | PS | 1 | 1 | [5 empty] | 1
540 | RACHERLA | MARKAPUR | GIDDALUR | KANIGIRI |  | 0835044 - M PPS,CHOLLAVEEDU(MAIN) | PS | 1 | 1 | [6 empty] | 1
541 | RACHERLA | MARKAPUR | GIDDALUR | KANIGIRI |  | 0835024 - MPPS,RACHERLA (KOTA) |  |  | 2 | [7 empty] | 2
542 | RACHERLA | MARKAPUR | GIDDALUR | KANIGIRI |  | 0835306 - MPUPS,GUDIMETLA |  |  | 1 | [7 empty] | 1
543 | RACHERLA | MARKAPUR | GIDDALUR | KANIGIRI |  | 0835602 - ZPHS,J.P.CHERUVU |  |  | 1 | [7 empty] | 1
| RACHERLA | [7 empty] | 10 | 0 | 2 | 1 | 0 | 0 | 1 | 2 | 4 | 0
544 | S.KONDA | KANDUKUR | KONDAPI | KANDUKUR | Chandrasekhar Reddy | 0856010 - MPPS,AVULAVARI PALEM | PS | Rural | 1 | [6 empty] | 1
545 | S.KONDA | KANDUKUR | KONDAPI | KANDUKUR | Chandrasekhar Reddy | 0856011 - MPPS,T.P.NAGAR | PS | Rural | 1 | [6 empty] | 1
546 | S.KONDA | KANDUKUR | KONDAPI | KANDUKUR | Chandrasekhar Reddy | 0856020 - MPPS,CHALLAMMAGIRI PATT | PS | Rural | 1 |  |  |  |  | 1
547 | S.KONDA | KANDUKUR | KONDAPI | KANDUKUR | Chandrasekhar Reddy | 0856021 -MPPS,POTHAIAHGARI PATTA PA | PS | Rural | 2 | [6 empty] | 2
548 | S.KONDA | KANDUKUR | KONDAPI | KANDUKUR | Chandrasekhar Reddy | 0856028 - MPPS,PEDANNAPALEM | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | Due to not Deposition of amount in favour of SMC the work could not be taken up
549 | S.KONDA | KANDUKUR | KONDAPI | KANDUKUR | Chandrasekhar Reddy | 0856051-GOVT PS,S.KONDA | PS | Rural | 2 | [6 empty] | 2
550 | S.KONDA | KANDUKUR | KONDAPI | KANDUKUR |  | 0856016 - MPPS,PAKALA (HP) |  |  | 1 | [7 empty] | 1
| S.KONDA | [7 empty] | 9 | 0 | 0 | 0 | 0 | 1 | 0 | 6 | 2 | 0 | 0 | 0 | 0
40 | S.MAGULUR | ONGOLE | ADDANKI | ADDANKI | SK.Rajan Babu | 0818002 - MPPS VELLALA CHERUVU (LE) | PS | Rural | 1 | [6 empty] | 1 |  |  | 1 | 0
41 | S.MAGULUR | ONGOLE | ADDANKI | ADDANKI | SK.Rajan Babu | 0818008 - MPPS SANTHAMAGULUR (CD) | PS | Rural | 2 | [6 empty] | 2 |  |  | 2 | 0
42 | S.MAGULUR | ONGOLE | ADDANKI | ADDANKI | SK.Rajan Babu | 0818022 - MPPS KOPPARAM AA | PS | Rural | 1 |  | 1 | [7 empty] | 1 | 0
43 | S.MAGULUR | ONGOLE | ADDANKI | ADDANKI | SK.Rajan Babu | 0818037 - MPPS KOMMALA PADU MG | PS | Rural | 1 | [6 empty] | 1 |  |  | 1 | 0
44 | S.MAGULUR | ONGOLE | ADDANKI | ADDANKI | SK.Rajan Babu | 0818039 - MPPS MAKKENAVARIPALEM(AA) | PS | Rural | 2 | [6 empty] | 2 |  |  | 2 | 0
45 | S.MAGULUR | ONGOLE | ADDANKI | ADDANKI | SK.Rajan Babu | 0818040 - MPPS MAKKENAVARIPALEM VC | PS | Rural | 1 |  |  | 1 | [6 empty] | 1 | 0
46 | S.MAGULUR | ONGOLE | ADDANKI | ADDANKI | SK.Rajan Babu | 0818604 - ZPHS MAKKENAVARIPALEM | HS | Rural | 1 | [6 empty] | 1 |  |  | 1 | 0
47 | S.MAGULUR | ONGOLE | ADDANKI | ADDANKI |  | 0818013 - MPPS PATHAMAGULUR DPEP |  |  | 1 | [7 empty] | 1
48 | S.MAGULUR | ONGOLE | ADDANKI | ADDANKI |  | 0818022 - MPPS KOPPARAM AA |  |  | 1 | [7 empty] | 1
| S.MAGULUR | [7 empty] | 11 | 0 | 1 | 1 | 0 | 0 | 0 | 7 | 2 | 0
560 | S.N.PADU | ONGOLE | S.N.PADU | ONGOLE | SK.Nazeer | 0843037 - MPPS,MANGAMURU (AA) | PS | Rural | 1 |  |  | 1
561 | S.N.PADU | ONGOLE | S.N.PADU | ONGOLE | SK.Nazeer | 0843045 - MPPS,NAWABPET,PERNAMETTA | PS | Rural | 1 |  |  | 1
562 | S.N.PADU | ONGOLE | S.N.PADU | ONGOLE | SK.Nazeer | 0843306 - MPUPS M VEMULAPADU | UPS | Rural | 1 |  |  |  | 1
563 | S.N.PADU | ONGOLE | S.N.PADU | ONGOLE | SK.Nazeer | 0843031 - MPPS,MATTI PADU | PS | Rural | 1 |  |  |  | 1
564 | S.N.PADU | ONGOLE | S.N.PADU | ONGOLE | SK.Nazeer | 0843032 - MPPS,RAJUGARIPALEM | PS | Rural | 1 |  |  |  |  | 1
565 | S.N.PADU | ONGOLE | S.N.PADU | ONGOLE | SK.Nazeer | 0843004 - MPPS,MYNAMPADU | PS | 1 | 1 |  |  |  | 1
566 | S.N.PADU | ONGOLE | S.N.PADU | ONGOLE | SK.Nazeer | 0843610 - APRS GANGAVARAM |  |  | 5 | [7 empty] | 5 |  |  |  |  | Site is to be finalized(Mahila Pranganam)waiting orders from collector.
| S.N.PADU | [7 empty] | 11 | 0 | 0 | 2 | 3 | 1 | 0 | 0 | 5 | 0
567 | TALLUR | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0815009 - MPPS LINGALAPADU | PS | Rural | 1 | [6 empty] | 1 |  |  | 1 | 0
568 | TALLUR | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0815010 - MPPS CHINTHALAPALEM | PS | Rural | 1 |  |  | 1 | [6 empty] | 1 | 0
569 | TALLUR | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0815031 - MPPS BODDIKURA PADU BC | PS | Rural | 1 |  |  |  | 1 | [5 empty] | 1 | 0
570 | TALLUR | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0815302 - MPUPS TURAKAPALEM | UPS | Rural | 1 |  |  | 1 | [6 empty] | 1 | 0
571 | TALLUR | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0815303 - MPUPS RAJANAGARAM | UPS | Rural | 1 |  |  | 1 | [6 empty] | 1 | 0
572 | TALLUR | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0815025 - MPPS KOTTUR OF LAKKAVARAM | PS | Rural | 1 |  |  | 1 | [6 empty] | 1 | 0
573 | TALLUR | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0815038 - MPPS SIVARAMAPURAM GEN | PS | 1 | 1 | [7 empty] | 1 |  | #REF! | #REF! | Courtcase | Site Dispute
574 | TALLUR | KANDUKUR | DARSI | ADDANKI | Ch.John Wilson | 0815604 - ZPHS SIVARAMURAM |  |  | 2 | [7 empty] | 2 |  |  |  | Courtcase
575 | TALLUR | KANDUKUR | DARSI | ADDANKI |  | 0815304 - MPUPS MADHAVARAM |  |  | 1 | [7 empty] | 1
576 | TALLUR | KANDUKUR | DARSI | ADDANKI |  | 0815602 - ZPHS EAST GANGAVARAM |  |  | 1 | [7 empty] | 1
| TALLUR | [7 empty] | 11 | 0 | 0 | 4 | 1 | 0 | 0 | 1 | 5 | 0
577 | TANGUTUR | ONGOLE | KONDAPI | KANDUKUR | Chandrasekhar Reddy | 0848011 - MPPS,TANGUTUR B C COLONY | PS | Rural | 1 | [7 empty] | 1
578 | TANGUTUR | ONGOLE | KONDAPI | KANDUKUR | Chandrasekhar Reddy | 0848017 - MPPS,PASUKUDURU | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | Not Requied
579 | TANGUTUR | ONGOLE | KONDAPI | KANDUKUR | Chandrasekhar Reddy | 0848028 - MPPS,VALLUR | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | Dismantling
580 | TANGUTUR | ONGOLE | KONDAPI | KANDUKUR | Chandrasekhar Reddy | 0848047 - MPPS,PONDUR (HW) | PS | Rural | 1 | [5 empty] | 1
581 | TANGUTUR | ONGOLE | KONDAPI | KANDUKUR | Chandrasekhar Reddy | 0848049 - MPPS,LAKSHMAKKAPALEM | PS | Rural | 1 |  | 1
582 | TANGUTUR | ONGOLE | KONDAPI | KANDUKUR | Chandrasekhar Reddy | 0848302 - MPUPS,VASEPALLIPADU | UPS | Rural | 3 | [7 empty] | 3 |  |  |  |  | Dismantling
583 | TANGUTUR | ONGOLE | KONDAPI | KANDUKUR | Chandrasekhar Reddy | 0848029 - MPPS,VALLUR (CE) | PS | Rural | 1 | [6 empty] | 1
584 | TANGUTUR | ONGOLE | KONDAPI | KANDUKUR | Chandrasekhar Reddy | 0848058 - G V V K S,VENKATAYA PALEM | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | Not Requied
585 | TANGUTUR | ONGOLE | KONDAPI | KANDUKUR | Chandrasekhar Reddy | 0848061-GOVT PS,TANGUTUR | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | No Site
586 | TANGUTUR | ONGOLE | KONDAPI | KANDUKUR | Chandra Sekhar Reddy | 0848610 - GOVT.HS, TANGUTUR (VILL) |  |  | 2 | [7 empty] | 2 |  |  |  |  | Due to not Deposition of amount in favour of SMC the work could not be taken up
587 | TANGUTUR | ONGOLE | KONDAPI | KANDUKUR |  | 0848036 - MPPS,MARLAPADU (CE) |  |  | 3 | [7 empty] | 3 |  |  |  |  | Not required
| TANGUTUR | [7 empty] | 16 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 13 | 0
588 | TARLAPADU | KANDUKUR | MARKAPUR | MARKAPUR | MUZEEB | 0810007 - MPPS POTHALAPADU AA | PS | Rural | 1 | [6 empty] | 1
589 | TARLAPADU | KANDUKUR | MARKAPUR | MARKAPUR | MUZEEB | 0810024 - MPPS TARLUPADU DPEP | PS | Rural | 1 | [7 empty] | 1
590 | TARLAPADU | KANDUKUR | MARKAPUR | MARKAPUR | MUZEEB | 0810033 - MPPS TADIVARI PALLI DPEP | PS | Rural | 1 | [7 empty] | 1
591 | TARLAPADU | KANDUKUR | MARKAPUR | MARKAPUR | MUZEEB | 0810301 - MPUPS SEETANAGULAVARAM | UPS | Rural | 1 | [6 empty] | 1
592 | TARLAPADU | KANDUKUR | MARKAPUR | MARKAPUR | MUZEEB | 0810306 - MPUPS GOLLA PALLI | UPS | Rural | 1 | [6 empty] | 1
593 | TARLAPADU | KANDUKUR | MARKAPUR | MARKAPUR | MUZEEB | 0810313 - MPUPS RAGASAMUDRAM | UPS | Rural | 1 | [6 empty] | 1
594 | TARLAPADU | KANDUKUR | MARKAPUR | MARKAPUR | MUZEEB | 0810314 - MPUPS MANGALA KUNTA | UPS | Rural | 1 | [6 empty] | 1
595 | TARLAPADU | KANDUKUR | MARKAPUR | MARKAPUR | MUZEEB | 0810014 - MPPS JANGAMREDDI PALLI | PS | Rural | 1 | [7 empty] | 1
596 | TARLAPADU | KANDUKUR | MARKAPUR | MARKAPUR | MUZEEB | 0810031 - MPPS UMMAREDDI PALLI | PS | Rural | 1 | [6 empty] | 1
597 | TARLAPADU | KANDUKUR | MARKAPUR | MARKAPUR | MUZEEB | 0810038 - MPPS KOTTUR | PS | Rural | 1 | [6 empty] | 1
598 | TARLAPADU | KANDUKUR | MARKAPUR | MARKAPUR | MUZEEB | 0810043 - MPPS SEETANAGULAVARAM | PS | Rural | 1 | [6 empty] | 1
599 | TARLAPADU | KANDUKUR | MARKAPUR | MARKAPUR | MUZEEB | 0810025 - MPPS MEERJA PETA | PS | 1 | 1 | [6 empty] | 1
600 | TARLAPADU | KANDUKUR | MARKAPUR | MARKAPUR | MUZEEB | 0810608 - ZPHS TADIVARI PALLI |  |  | 2 | [6 empty] | 2
| TARLAPADU | [7 empty] | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 3 | 0 | 0 | 0 | 0
601 | TRIPURANTHAKAM | MARKAPUR | Y.PALEM | MARKAPUR | SURESH | 0803001 - MPPS DUVVALI | PS | Rural | 2 |  |  |  |  | 1 |  | 1
602 | TRIPURANTHAKAM | MARKAPUR | Y.PALEM | MARKAPUR | SURESH | 0803004 - MPPS GANAPAVARAM(MAIN) | PS | Rural | 2 | [6 empty] | 2
603 | TRIPURANTHAKAM | MARKAPUR | Y.PALEM | MARKAPUR | SURESH | 0803010 - MPPS VENGAYAPALEM | PS | Rural | 1 | [6 empty] | 1
604 | TRIPURANTHAKAM | MARKAPUR | Y.PALEM | MARKAPUR | SURESH | 0803012 - MPPS G.UMMADIVARAM RAMALA | PS | Rural | 1 |  |  |  |  | 1
605 | TRIPURANTHAKAM | MARKAPUR | Y.PALEM | MARKAPUR | SURESH | 0803016 - MPPS NADIPALEM | PS | Rural | 1 | [6 empty] | 1
606 | TRIPURANTHAKAM | MARKAPUR | Y.PALEM | MARKAPUR | SURESH | 0803018 - MPPS BONKURIVARI PALEM | PS | Rural | 1 | [6 empty] | 1
607 | TRIPURANTHAKAM | MARKAPUR | Y.PALEM | MARKAPUR | SURESH | 0803019 - MPPS D.V.N.COLONY | PS | Rural | 1 | [6 empty] | 1
608 | TRIPURANTHAKAM | MARKAPUR | Y.PALEM | MARKAPUR | SURESH | 0803020 - MPPS KOTHA MUDIVEMULA | PS | Rural | 1 | [6 empty] | 1
609 | TRIPURANTHAKAM | MARKAPUR | Y.PALEM | MARKAPUR | SURESH | 0803028-MPPS TRIPURANTHAKAM(NSC) | PS | Rural | 1 |  |  | 1
610 | TRIPURANTHAKAM | MARKAPUR | Y.PALEM | MARKAPUR | SURESH | 0803030 - MPPS NASARREDDY NAGAR | PS | Rural | 1 |  |  | 1
611 | TRIPURANTHAKAM | MARKAPUR | Y.PALEM | MARKAPUR | SURESH | 0803031 - MPPS SUGALI THANDA | PS | Rural | 1 | [6 empty] | 1
612 | TRIPURANTHAKAM | MARKAPUR | Y.PALEM | MARKAPUR | SURESH | 0803035 - MPPS LELLAPALLI | PS | Rural | 2 | [6 empty] | 2
613 | TRIPURANTHAKAM | MARKAPUR | Y.PALEM | MARKAPUR | SURESH | 0803039 - MPPS DIVEPALLI | PS | Rural | 1 | [6 empty] | 1
614 | TRIPURANTHAKAM | MARKAPUR | Y.PALEM | MARKAPUR | SURESH | 0803040 - MPPS GOLLAVANDLA PALLI | PS | Rural | 1 | [6 empty] | 1
615 | TRIPURANTHAKAM | MARKAPUR | Y.PALEM | MARKAPUR | SURESH | 0803302 - MPUPS ENDURIVARI PALEM | UPS | Rural | 1 | [6 empty] | 1
616 | TRIPURANTHAKAM | MARKAPUR | Y.PALEM | MARKAPUR | SURESH | 0803308 - MPUPS VISWANADHAPURAM | UPS | Rural | 1 |  | 1
617 | TRIPURANTHAKAM | MARKAPUR | Y.PALEM | MARKAPUR | SURESH | 0803311 - MPUPS KANKANALA PALLI | UPS | Rural | 3 | [6 empty] | 3
618 | TRIPURANTHAKAM | MARKAPUR | Y.PALEM | MARKAPUR | SURESH | 0803310 - MPUPS NADIGADDA | UPS | 1 | 1 |  | 1
619 | TRIPURANTHAKAM | MARKAPUR | Y.PALEM | MARKAPUR | SURESH | 0803606 - APRES GANAPAVARAM |  |  | 4 |  |  | 4
620 | TRIPURANTHAKAM | MARKAPUR | Y.PALEM | MARKAPUR |  | 0803304 - MPUPS SOMEPALLI |  |  | 1 |  | 1
621 | TRIPURANTHAKAM | MARKAPUR | Y.PALEM | MARKAPUR |  | 0803311 - MPUPS KANKANALAPALLI |  |  | 1 |  |  | 1
| TRIPURANTHAKAM | [7 empty] | 29 | 0 | 3 | 7 | 0 | 2 | 0 | 17 | 0 | 0
622 | ULAVAPADU | KANDUKUR | KANDUKUR | KANDUKUR | Venkateswara Rao | 0855031 - MPPS,ULAVAPADU(KOTHURU) | PS | Rural | 1 |  |  | 1
623 | ULAVAPADU | KANDUKUR | KANDUKUR | KANDUKUR | Venkateswara Rao | 0855037 - MPPS,BADDIPUDI(KMP) | PS | Rural | 1 |  |  |  | 1
624 | ULAVAPADU | KANDUKUR | KANDUKUR | KANDUKUR | Venkateswara Rao | 0855038 - MPPS,BADDIPUDI (PMP) | PS | Rural | 1 |  |  |  | 1
625 | ULAVAPADU | KANDUKUR | KANDUKUR | KANDUKUR | Venkateswara Rao | 0855039 - MPPS,KRISHNA PURAM | PS | Rural | 1 |  |  |  | 1
626 | ULAVAPADU | KANDUKUR | KANDUKUR | KANDUKUR | Venkateswara Rao | 0855041 - MPPS,VEEREPALLI YC (WEST) | PS | Rural | 1 |  |  | 1
627 | ULAVAPADU | KANDUKUR | KANDUKUR | KANDUKUR | Venkateswara Rao | 0855049 - MPPS,ANKAMPALEM(CKC) | PS | Rural | 1 | [7 empty] | 1 |  |  |  |  | Not Requied
628 | ULAVAPADU | KANDUKUR | KANDUKUR | KANDUKUR | Venkateswara Rao | 0855053 - MPPS,PALLEPALEM(RP) | PS | Rural | 1 |  | 1
629 | ULAVAPADU | KANDUKUR | KANDUKUR | KANDUKUR | Venkateswara Rao | 0855301 - MPUPS,ALAGAYA PALEM | UPS | Rural | 1 | [6 empty] | 1
630 | ULAVAPADU | KANDUKUR | KANDUKUR | KANDUKUR | Venkateswara Rao | 0855302 - MPUPS,K.RAJUPALEM | UPS | Rural | 1 | [7 empty] | 1 |  |  |  |  | Dismantling
631 | ULAVAPADU | KANDUKUR | KANDUKUR | KANDUKUR | Venkateswara Rao | 0855303 - MPUPS,VEEREPALLI | UPS | Rural | 1 |  |  | 1
632 | ULAVAPADU | KANDUKUR | KANDUKUR | KANDUKUR | Venkateswara Rao | 0855304 - MPUPS,CHAGALLU | UPS | Rural | 1 |  |  |  | 1
633 | ULAVAPADU | KANDUKUR | KANDUKUR | KANDUKUR | Venkateswara Rao | 0855308 - MPUPS,MANNETIKOTA | UPS | Rural | 1 |  |  | 1
634 | ULAVAPADU | KANDUKUR | KANDUKUR | KANDUKUR | Venkatesarlu | 0855602 - ZPHS BHEEMAVARAM |  |  | 2 |  |  | 2
| ULAVAPADU | [7 empty] | 14 | 0 | 1 | 6 | 4 | 0 | 0 | 1 | 2 | 0
635 | V.V.PALEM | KANDUKUR | KANDUKUR | KANDUKUR | Ramesh Babu | 0851002 - MPPS,GARUKUPALEM | PS | Rural | 1 |  |  |  | 1
636 | V.V.PALEM | KANDUKUR | KANDUKUR | KANDUKUR | Ramesh Babu | 0851005 - MPPS,VEERANNA PALEM | PS | Rural | 1 |  |  |  | 1
637 | V.V.PALEM | KANDUKUR | KANDUKUR | KANDUKUR | Ramesh Babu | 0851041 - MPPS,SINGAMAENI PALLE | PS | Rural | 1 |  |  |  | 1
638 | V.V.PALEM | KANDUKUR | KANDUKUR | KANDUKUR | Ramesh Babu | 0851044 - MPPS,NALADALAPUR(HP) | PS | Rural | 1 |  |  | 1
639 | V.V.PALEM | KANDUKUR | KANDUKUR | KANDUKUR | Ramesh Babu | 0851301 - MPUPS,ANKABHUPALAPURAM | UPS | Rural | 1 |  |  |  | 1
640 | V.V.PALEM | KANDUKUR | KANDUKUR | KANDUKUR | Ramesh Babu | 0851303 - MPUPS,CHUNDI | UPS | Rural | 1 |  |  |  | 1
641 | V.V.PALEM | KANDUKUR | KANDUKUR | KANDUKUR | Ramesh Babu | 0851304 - MPUPS,KONDASAMUDRAM | UPS | Rural | 1 | [6 empty] | 1
642 | V.V.PALEM | KANDUKUR | KANDUKUR | KANDUKUR | Ramesh Babu | 0851308 - MPUPS,POLINENI CHERUVU | UPS | Rural | 1 |  |  |  | 1
643 | V.V.PALEM | KANDUKUR | KANDUKUR | KANDUKUR | Ramesh Babu | 0851303 - MPUPS,CHUNDI | UPS | 1 | 1 |  |  |  | 1
644 | V.V.PALEM | KANDUKUR | KANDUKUR | KANDUKUR |  | 0851007 - MPPS,LINGAPALEM(GEN) |  |  | 1 | [7 empty] | 1
645 | V.V.PALEM | KANDUKUR | KANDUKUR | KANDUKUR |  | 0851601 - ZPHS,VOLETIVARI PALEM |  |  | 1 | [7 empty] | 1
646 | V.V.PALEM | KANDUKUR | KANDUKUR | KANDUKUR |  | 0851604 - ZPHS,SAKHAVARAM |  |  | 2 | [7 empty] | 2
| V.V.PALEM | [7 empty] | 13 | 0 | 0 | 1 | 7 | 0 | 0 | 1 | 4 | 0
647 | VELIGANDLA | KANDUKUR | KANIGIRI | KANIGIRI |  | 0839008 - MPPS,P.RALLA PALLI | PS | Rural | 1 | [6 empty] | 1
648 | VELIGANDLA | KANDUKUR | KANIGIRI | KANIGIRI |  | 0839014 MPPS,KANKANAM PADU(G) | PS | Rural | 1 | [6 empty] | 1
649 | VELIGANDLA | KANDUKUR | KANIGIRI | KANIGIRI |  | 0839018 - MPPS,K AGRAHARAM | PS | Rural | 2 |  |  |  |  | 2
650 | VELIGANDLA | KANDUKUR | KANIGIRI | KANIGIRI |  | 0839027 - MPPS,PADMAPURAM | PS | Rural | 1 | [6 empty] | 1
651 | VELIGANDLA | KANDUKUR | KANIGIRI | KANIGIRI |  | 0839045 - MPPS,PAPAYAPALLI | PS | Rural | 3 | [5 empty] | 3
652 | VELIGANDLA | KANDUKUR | KANIGIRI | KANIGIRI |  | 0839057 - MPPS,J.N.PALLI | PS | Rural | 1 |  |  |  |  | 1
653 | VELIGANDLA | KANDUKUR | KANIGIRI | KANIGIRI |  | 0839306 - MPUPS,P.RALLA PALLI | UPS | Rural | 1 |  |  | 1
654 | VELIGANDLA | KANDUKUR | KANIGIRI | KANIGIRI |  | 0839309 - M P U P S,KOTALA PALLI | UPS | Rural | 1 | [7 empty] | 1 |  |  |  |  | No strenth
655 | VELIGANDLA | KANDUKUR | KANIGIRI | KANIGIRI |  | 0839005-MPPS,GUMMALLAKARRA(CHURCH) | PS | Rural | 1 | [5 empty] | 1
656 | VELIGANDLA | KANDUKUR | KANIGIRI | KANIGIRI |  | 0839013 - MP PS,CHENNAMPALLI | PS | Rural | 1 |  |  |  | 1
657 | VELIGANDLA | KANDUKUR | KANIGIRI | KANIGIRI |  | 0839028 - MPPS,BONTHAGUNTA PALLI | PS | Rural | 1 | [6 empty] | 1
658 | VELIGANDLA | KANDUKUR | KANIGIRI | KANIGIRI |  | 0839039-MPPS,RAMAGOPALAPURAM | PS | Rural | 1 |  |  |  |  | 1
659 | VELIGANDLA | KANDUKUR | KANIGIRI | KANIGIRI |  | 0839052 - MPPS,KOTALAPALLI(SOUTH) | PS | Rural | 1 | [6 empty] | 1
660 | VELIGANDLA | KANDUKUR | KANIGIRI | KANIGIRI |  | 0839309 - M P U P S,KOTALA PALLI |  |  | 1 | [7 empty] | 1
661 | VELIGANDLA | KANDUKUR | KANIGIRI | KANIGIRI |  | 0839604-ZPHS,IMMADICHERUVU |  |  | 1 |  |  |  |  | 1
| VELIGANDLA | [7 empty] | 18 | 0 | 0 | 1 | 1 | 5 | 4 | 5 | 2 | 0
662 | VETAPALEM | ONGOLE | CHIRALA | PARCHUR |  | 0824004 - MPPS ANUMALLAPET(S) | PS | Rural | 1 | 5.3 | [6 empty] | 1 |  |  |  |  | Old building to be Dismantling
663 | VETAPALEM | ONGOLE | CHIRALA | PARCHUR |  | 0824006 - MPPS.BAPAIAH NAGAR | PS | Rural | 1 | 5.3 | [5 empty] | 1
664 | VETAPALEM | ONGOLE | CHIRALA | PARCHUR |  | 0824011 - MPPS NELAKANTAPURAM | PS | Rural | 1 | 5.3 | [6 empty] | 1 |  |  |  |  | No Site
665 | VETAPALEM | ONGOLE | CHIRALA | PARCHUR |  | 0824020 - MPPS BATCHULAVARI PALEM | PS | Rural | 1 | 5.3 | [5 empty] | 1
666 | VETAPALEM | ONGOLE | CHIRALA | PARCHUR |  | 0824026 - MPPS CHALLAREDDY PALEM | PS | Rural | 1 | 5.3 |  |  |  | 1
667 | VETAPALEM | ONGOLE | CHIRALA | PARCHUR |  | 0824030 - MPPS VEDDESANGAM | PS | Rural | 1 | 5.3 |  | 1
668 | VETAPALEM | ONGOLE | CHIRALA | PARCHUR |  | 0824039 - C.A.MPPRIMARY. S | PS | Rural | 1 | 5.3 | [5 empty] | 1
669 | VETAPALEM | ONGOLE | CHIRALA | PARCHUR |  | 0824042 - GPS JAGANNADHA PURAM | PS | Rural | 1 | 5.3 | [6 empty] | 1 |  |  |  |  | Not Requied
670 | VETAPALEM | ONGOLE | CHIRALA | PARCHUR |  | 0824302 - MPUPS PAPAYA PALEM | UPS | Rural | 1 | 5.3 |  | 1
671 | VETAPALEM | ONGOLE | CHIRALA | PARCHUR |  | 0824608-A.P.R.S,BC BOYS,VETAPALEM | HSS | Rural | 6 | 31.8 | [5 empty] | 6
672 | VETAPALEM | ONGOLE | CHIRALA | PARCHUR |  | 0824307 - MPUPS KOTHAPET (Y.C) | UPS | 1 | 1 | 5.3 | [6 empty] | 1
| VETAPALEM | [7 empty] | 16 | 84.8 | 0 | 2 | 0 | 1 | 0 | 9 | 4 | 0
673 | Y.PALEM | MARKAPUR | Y.PALEM | MARKAPUR | MAHESH | 0801002 - MPPS YALLAREDDY PALLI | PS | Rural | 2 | [6 empty] | 2
674 | Y.PALEM | MARKAPUR | Y.PALEM | MARKAPUR | MAHESH | 0801003 - MPPS GADDAMEEDI PALLI | PS | Rural | 1 | [6 empty] | 1
675 | Y.PALEM | MARKAPUR | Y.PALEM | MARKAPUR | MAHESH | 0801008 - MPPS REGULAPALLI | PS | Rural | 1 |  |  | 1
676 | Y.PALEM | MARKAPUR | Y.PALEM | MARKAPUR | MAHESH | 0801014 - MPPS YERRAGONDAPALEM | PS | Rural | 4 |  |  | 2 | 2
677 | Y.PALEM | MARKAPUR | Y.PALEM | MARKAPUR | MAHESH | 0801015 - MPPS AMBEDKAR NAGAR | PS | Rural | 1 | [6 empty] | 1
678 | Y.PALEM | MARKAPUR | Y.PALEM | MARKAPUR | MAHESH | 0801021 - MPPS YERRAGONDAPALEM | PS | Rural | 2 | [6 empty] | 2
679 | Y.PALEM | MARKAPUR | Y.PALEM | MARKAPUR | MAHESH | 0801022 - MPPS CHENNARAYUNI PALLI | PS | Rural | 1 | [7 empty] | 1
680 | Y.PALEM | MARKAPUR | Y.PALEM | MARKAPUR | MAHESH | 0801035 - MPPS AMMANIGUDIPADU | PS | Rural | 1 |  |  | 1
681 | Y.PALEM | MARKAPUR | Y.PALEM | MARKAPUR | MAHESH | 0801040 - MPPS AMMANIGUDIPADU (ST BC) | PS | Rural | 2 |  |  | 2
682 | Y.PALEM | MARKAPUR | Y.PALEM | MARKAPUR | MAHESH | 0801046 - APTWRS(G) MILLAMPALLI | PS | Rural | 1 | [6 empty] | 1
683 | Y.PALEM | MARKAPUR | Y.PALEM | MARKAPUR | MAHESH | 0801047 - GOVT.ASHRAMA S ALLI PALEM | PS | Rural | 2 | [7 empty] | 2 |  |  |  |  | The village is depopulated and new site will be procured at new village
684 | Y.PALEM | MARKAPUR | Y.PALEM | MARKAPUR | MAHESH | 0801063 - GOVT PS GANJIVARI PALLI | PS | Rural | 1 |  |  | 1
685 | Y.PALEM | MARKAPUR | Y.PALEM | MARKAPUR | MAHESH | 0801301 - MPUPS GANJIVARI PALLI | UPS | Rural | 2 | [6 empty] | 2
686 | Y.PALEM | MARKAPUR | Y.PALEM | MARKAPUR | MAHESH | 0801313 - MPUPS VADAMPALLI | UPS | Rural | 1 |  |  | 1
687 | Y.PALEM | MARKAPUR | Y.PALEM | MARKAPUR | MAHESH | 0801006 - MPPS JANGAMVARI PALLI | PS | Rural | 1 |  | 1
688 | Y.PALEM | MARKAPUR | Y.PALEM | MARKAPUR | MAHESH | 0801019 - MPPS CHERLO THANDA | PS | Rural | 1 |  |  |  | 1
689 | Y.PALEM | MARKAPUR | Y.PALEM | MARKAPUR | MAHESH | 0801055 - GOVT PS YERRAGONDAPALEM | PS | Rural | 1 |  |  | 1
690 | Y.PALEM | MARKAPUR | Y.PALEM | MARKAPUR | MAHESH | 0801060 - GOVT PS A C GUDEM | PS | Rural | 1 | [6 empty] | 1
691 | Y.PALEM | MARKAPUR | Y.PALEM | MARKAPUR | MAHESH | 0801075-GOVT PS HANUMANTHUNI GUDEM | PS | Rural | 1 |  |  | 1
692 | Y.PALEM | MARKAPUR | Y.PALEM | MARKAPUR | MAHESH | 0801041 - MPPS GURRAPUSALA | PS | 1 | 1 |  |  |  | 1
693 | Y.PALEM | MARKAPUR | Y.PALEM | MARKAPUR | MAHESH | 0801057 - MPPS VEERABHADRA PURAM | PS | 1 | 1 | [6 empty] | 1
694 | Y.PALEM | MARKAPUR | Y.PALEM | MARKAPUR | MAHESH | 0801314 - MPUPS KOTHAPALLI | UPS | 1 | 1 | [6 empty] | 1
| Y.PALEM | [7 empty] | 30 | 0 | 1 | 10 | 4 | 0 | 0 | 12 | 3 | 0
695 | YEDDANAPUDI | ONGOLE | PARCHUR | PARCHUR |  | 0819019 - MPPS YEDDANA PUDI (HC) |  |  | 1 | [7 empty] | 1
696 | YEDDANAPUDI | ONGOLE | PARCHUR | PARCHUR |  | 0819024 - MPPS CH PADU MARTUR ROAD |  |  | 1 | [7 empty] | 1
697 | YEDDANAPUDI | ONGOLE | PARCHUR | PARCHUR |  | 0819027 - MPPS GANNAVARAM SC |  |  | 1 | [7 empty] | 1
| YEDDANAPUDI | [7 empty] | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
698 | ZARUGUMILLI | KANDUKUR | KONDAPI | KANDUKUR | Chandrasekhar Reddy | 0849029 - MPPS,ZARUGUMALLI (GEN) | PS | Rural | 1 |  |  | 1
699 | ZARUGUMILLI | KANDUKUR | KONDAPI | KANDUKUR | Chandrasekhar Reddy | 0849032 - MPPS,ZARUGUMALLI (VC) | PS | Rural | 1 |  |  | 1
700 | ZARUGUMILLI | KANDUKUR | KONDAPI | KANDUKUR | Chandrasekhar Reddy | 0849305 - M.P.U.PS,PEERAPURAM | UPS | Rural | 1 |  | 1
701 | ZARUGUMILLI | KANDUKUR | KONDAPI | KANDUKUR | Chandrasekhar Reddy | 0849007 - MPPS,KAMEPALLI AGRAHARAM | PS | Rural | 1 |  |  | 1
702 | ZARUGUMILLI | KANDUKUR | KONDAPI | KANDUKUR | Chandrasekhar Reddy | 0849013 - MPPS,JANARDHANAPURAM | PS | Rural | 1 | [6 empty] | 1
703 | ZARUGUMILLI | KANDUKUR | KONDAPI | KANDUKUR | Chandrasekhar Reddy | 0849029 - MPPS,ZARUGUMALLI (GEN) | PS | 1 | 1 |  |  | 1
| ZARUGUMILLI | [7 empty] | 6 | 0 | 1 | 4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
[6 empty] | Total |  |  | 1724 | 572.4 | 82 | 356 | 180 | 108 | 54 | 528 | 416 | 0 | #REF! | #REF! | 0 | 0