## SATR 1
SAUDI ARAMCO ID/PIEU-31-August-2018 - REV.2018.08.00 (Standards Cutoff - August 31,2018) | [25 empty] | Rev. 2018.06.00 30 June 2018
SAUDI ARAMCO TEST REPORT | [16 empty] | SATR NUMBER |  |  |  | DATE APPROVED |  |  |  |  | QR NUMBER | [5 empty] | REPORT DATE
WEEKLY WELDER REPAIR RATE REPORT | [16 empty] | SATR-W-2013
PROJECT TITLE | [8 empty] | WBS/BI/JO NUMBER | [8 empty] | CONT./SUB-CONT.
ARAMCO PIPING | [8 empty] | A101
SAUDI ARAMCO USE ONLY
SATIP NUMBER |  | SATIP ACTIVITY NUMBER | [6 empty] | CONTRACTOR INSP LEVEL |  |  |  |  | SUB-CONTRACTOR INSP LEVEL |  |  |  |  | ARAMCO INSPECTION LEVEL |  |  |  |  | QTY INSP |  | MH's SPENT |  |  |  | TRAVEL TIME
From |  | 2020-04-28 |  |  |  | To |  |  | 2020-05-02
WEEKLY WELDER REPAIR RATE REPORT
ITEM | WELDERS NAME | SYMBOL | LINEAR/JOINT BASIS | [29 empty] | Remarks
|  |  | THIS WEEK -JOINT BASIS | [6 empty] | CUMULATIVE-JOINT BASIS | [7 empty] | THIS WEEK -LINEAR BASIS | [7 empty] | CUMULATIVE- LINEAR BASIS
|  |  | NUMBER JOINTS WELDED |  | NUMBER JOINTS RT |  | NUMBER JOINTS REJECTED |  | REJECT % JOINT | NUMBER JOINTS WELDED |  | NUMBER JOINTS RT |  |  | NUMBER OF JOINTS REJECTED |  | REJECT % JOINT | NUMBER INCHES WELDED |  | NUMBER INCHES RT |  | NUMBER INCHES REJECTED |  | REJECT % INCHES |  | NUMBER INCHES WELDED |  | NUMBER INCHES RT |  | NUMBER INCHES REJECTED |  | REJECT % INCHES
|  |  | 100% | 10% | 100% | 10% | 100% | 10% |  | 100% | 10% | 100% | 10% |  | 100% | 10% |  | 100% | 10% | 100% | 10% | 100% | 10% |  |  | 100% | 10% | 100% | 10% | 100% | 10%
1 | WAQAR RAHMAN | C-161 | 2 | 0 | 0 | 0 | 0 | 0 | 0 - 0 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 - 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 - 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 - 0
2 | K VENKATESH | W-101 | 1 | 0 | 0 | 0 | 0 | 0 | 0 - 0 | 1 | 0 | 0 | 0 |  | 0 | 0 | 0 - 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 - 0 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 - 0
3 | ABDUL SAYEED | W-109 | 1 | 0 | 1 | 0 | 0 | 0 | 0 - 0 | 1 | 0 | 1 | 0 |  | 0 | 0 | 0 - 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 - 0 |  | 4 | 0 | 4 | 0 | 0 | 0 | 0 - 0
PREPARED BY: | [6 empty] | VERIFIED BY: | [8 empty] | REVIEWED AND APPROVED BY: | [8 empty] | REVIEWED BY:
CONSTRUCTION REPRESENTATIVE | [6 empty] | QC INSPECTOR or SUPERVISOR | [8 empty] | SAPMT REPRESENTATIVE-REVIEWED BY | [8 empty] | PID REPRESENTITIVE
NAME: | [6 empty] | NAME: | [8 empty] | NAME: | [8 empty] | NAME:
SIGN: | [6 empty] | SIGN: | [8 empty] | SIGN: | [8 empty] | SIGN:
DATE: | [6 empty] | DATE: | [8 empty] | DATE: | [8 empty] | DATE: