**2022 F3RES International Task List**

**As of 15 March**

**Next Meeting: Tuesday, 15 March, 7PM**

 **Home of Greg McGill**

Dates: 11-12-13 June, 2022 Venue: Balloon Fiesta Park, Panel D6

**Contest Director: Dan R. and Jan C.**

 Announcements on site

POC for all emergencies; Emergency Action Plan

Decision point for start, stop, delays, cancellation

AMA Sanction and After-action report (Sanction in Hand)

Sign-up sheets

RCGroups Post (Done)

Coordinator with BFP

**Flying Site Manager: Greg**

 Hi-starts (Retrieve planned for 19 March)

Landing Tapes (Retrieve planned for 19 March)

Tape Measures (Retrieve planned for 19 March)

Canopies for score keeper, food, HQ (Retrieve planned for 19 March)

Tables: Score Keeper, Sign-up Sheets, Food Service (yeah, 19 March)

First-aid Kit

Assist set-up

**Time/Score-keeping: Richard and Tom T.**

Computers, printers

Glider Score

Speakers, PA and Amplifier

Flight Matrix

Clocks and Batteries

**On-Site Refreshments: TBD**

Drink: water and non-carbonated drinks

Coolers and ice chests

Lunch Makings

**Sanitation: TBD**

Porta Pottie

Trash bags and cleanup

**Awards and Decorations: Dan R.**

First-thru-third trophies

Certificates: top-scoring team, highest-scoring Yellow Jacket

**Finances: Richard Shagam**

On-LineRegistration

 Matrix

 Money

 Flier for Web Site, also for District VII web site.

**Richard and Dan R. to locate/secure storage unit for club equipment near BFP**